## Summary
Count |  | Row Labels | Count of State
Installation Status | Total | Goa | 3
Installed & Live | 113 | Installed & Live | 2
Router with Engg Mr. Harkesh ATM machine Lan Cable has been cut by a rat; after the problem is fixed, please confirm with us so that we may start the installation. | 1 | OEM schedule still not received | 1
WIP OEM Confirmation Awaited (Our Router LIVE on 22-02-2024) | 1 | Maharashtra | 112
Grand Total | 115 | Held Up | 1
|  | Installed & Live | 98
|  | Kept on hold by BM due to renovation work | 2
|  | machine under shifting | 1
|  | material not received | 2
|  | network issue at site | 2
|  | No Network | 2
|  | OEM was ready but our team will attend on Monday | 1
|  | Planned today but OEM denied | 2
|  | Site Shifted to other location- Mini branch | 1
|  | Rajashthan | 15
|  | Installed & Live | 13
|  | WIP OEM Confirmation Awaited (Our Router LIVE on 22-02-2024) | 1
|  | Router with Engg Mr. Harkesh ATM machine Lan Cable has been cut by a rat; after the problem is fixed, please confirm with us so that we may start the installation. | 1
|  | Grand Total | 130

## Sheet1 (hidden)
Count of CSS BM | Column Labels
Row Labels | 2023-08-05 | 2023-08-10 | 2023-08-11 | 2023-08-14 | 2023-08-18 | 2023-08-19 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-28 | 2023-08-29 | 2023-08-30 | Grand Total
Jitendra C | [14 empty] | 1 | bar: 2023-08-18
Santosh Gawai | [14 empty] | 1 | bar: 2023-08-29
Harendra S | [14 empty] | 2 | bar: 2023-08-24 to 2023-08-25
Anil S | [14 empty] | 2 | bar: 2023-08-28 to 2023-08-29
Kunal K | [14 empty] | 2 | bar: 2023-08-28 to 2023-08-29
Bharat P | 2023-08-21: 2; 2023-08-22: 2 | 4
Ishwar | 2023-08-21: 1; 2023-08-23: 1; 2023-08-28: 2; 2023-08-29: 1 | 5
Utkarsh G | 2023-08-25: 2; 2023-08-29: 2; 2023-08-30: 1 | 5
Kailash R | 2023-08-18: 3; 2023-08-25: 2; 2023-08-28: 2 | 7
Kishore B | 2023-08-24: 1; 2023-08-25: 3; 2023-08-28: 2; 2023-08-30: 1 | 7
Ravikant D | 2023-08-18: 1; 2023-08-22: 4; 2023-08-23: 1; 2023-08-24: 2; 2023-08-25: 1 | 9
Jakindra P | 2023-08-22: 1; 2023-08-23: 2; 2023-08-28: 2; 2023-08-29: 5 | 10
Ashish J | 2023-08-05: 1; 2023-08-10: 2; 2023-08-11: 3; 2023-08-14: 4 | 10
Mahendra M | 2023-08-18: 2; 2023-08-21: 3; 2023-08-22: 1; 2023-08-23: 4; 2023-08-24: 1; 2023-08-25: 1; 2023-08-29: 1 | 13
Shankar G | 2023-08-18: 2; 2023-08-19: 1; 2023-08-21: 3; 2023-08-22: 4; 2023-08-23: 2; 2023-08-24: 5; 2023-08-25: 2 | 19
Grand Total | 1 | 2 | 3 | 4 | 9 | 1 | 9 | 12 | 10 | 10 | 12 | 10 | 12 | 2 | 97

## Master data
Sr No | MSP | Allocation Date | Assigned By | Project | Vertical | code | SR # | Bank | ATMID | IP | Address | City | State | CSS BM | Installation Status | Installaled Date | Sub Status/ETA | Follow-up Remarks | Engineer (Name & Number) | Schedule | Cost | Courier-Name | Tracking-Number | Delivery-Status | Security Seal Number | Sr. NO | Configuration Status | Handover to | Date Of Handover | REMARK | Router Faulty | Handover date | Handover Person | ms Vendor1 | ID on Make | Invoice No Invoice Date | Invoice Date
1 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router |  | - | SBI | S1BH001469028 | 10.130.1.26 | 493/267, SATPUR GANGAPUR LINK ROAD , ASHOK NAGAR, NASHIK - 422012 | Nashik | Maharashtra | Bharat P | Installed & Live | 2023-08-21 | - | - | Bharat P - 9657765388 | 2023-08-17 | - | By Bus | By Bus | Delivered | 653127 | 2120R502304260095 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
2 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BG000410001 | 10.130.0.174 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-25 | Site under Shifting | Installed at S1BB007339004 - University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Nana - 7875777801 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653111 | 2120R502304260093 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
3 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BH001469019 | #N/A | CDO, MERI COLONY, DINDORI ROAD, NASHIK - 422003 | Nashik | Maharashtra | Bharat P | No Network | NA | No Network | - | Bharat P - 9657765388 | 2023-08-17 | - | By Bus | By Bus | Delivered | 653117 | 2120R502304260097 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | No Network |  | NA | NA
4 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NG000454433 | 10.130.0.158 | DR. SUJATA RAVAT, 42/1, SHANTA CLINIC & GYM, NEAR SHIVRAJ SCHOOL, GANESH NAGAR, PUNE | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-18 | - | - | Mahesh Mahendra kamble - 9881996778 | 2023-08-18 | - | By Bus | By Bus | Delivered | 653112 | 2120R502304260118 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
5 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BB000410003 | 10.130.0.170 | KRISHI UTPANN BAJAR SAMITI, CHHANTRAPATI SHIVAJI MARKET YARD, RAJGURUNAGAR (KHED), PUNE 410505. | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-18 | - | - | Kiran gadhave - 9763838782 | 2023-08-18 | - | By Bus | By Bus | Delivered | 653115 | 2120R502304260107 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
6 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NG005392007 | 10.130.1.38 | NEAR GANGADHAR TALKIES, AT POST SINNAR , DIST NASHIK, PIN - 422103 | Nashik | Maharashtra | Bharat P | Installed & Live | 2023-08-22 | - | - | Bharat P - 9657765388 | 2023-08-17 | - | By Bus | By Bus | Delivered | 653130 | 2120R502304260176 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
7 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BW001469101 | 10.130.1.18 | POOJA AVENUE, SHANTI PARK, UPNAGAR, NASHIK - 422006 | Nashik | Maharashtra | Bharat P | Installed & Live | 2023-08-21 | - | - | Bharat P - 9657765388 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653126 | 2120R502304260116 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
8 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NW005539003 | #N/A | SBI PIMPALGAON BRANCH BLDG, DIST. NASHIK , PIMPALGAON - 422209 | Nashik | Maharashtra | Bharat P | Site Shifted to other location- Mini branch | NA | - | - | Bharat P - 9657765388 | 2023-08-19 | - | By Bus | By Bus | Delivered | 653129 | 2120R502304260131 | Done | Sandeep Prajapati | 2023-08-05 |  |  |  |  | Site Shifted to other location- Mini branch |  | NA | NA
9 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NW000454187 | 10.130.0.162 | SHOP NO.A/7, ARJUN PARK, KALE-PADAL ROAD, SASANENAGAR, PUNE 411028. LANDMARK: SBI SASANENAGAR BRANCH | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-18 | - | - | Abhijeet Chandrakant Kamlapure - 8888378457 | 2023-08-18 | - | By Bus | By Bus | Delivered | 653113 | 2120R502304260071 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
10 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NG000555005 | 10.130.0.166 | THE LONAWALA INDUSTRIAL ESTATE CO-OPERATIVE LTD. LONAWALA. 410401. LANDMARK: SBI IE LONAWALA BRANCH | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-25 | Site under Shifting | Installed at S10B007339003 - University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Nana - 7875777801 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653116 | 2120R502304260153 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
11 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BA000440001 | 10.130.1.30 | YEOLA ROAD, AT POST - VINCHUR, DIST. NASHIK PIN - 422306 | Nashik | Maharashtra | Bharat P | Installed & Live | 2023-08-22 | - | - | Bharat P - 9657765388 | 2023-08-19 | - | By Bus | By Bus | Delivered | 653128 | 2120R502304260126 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
12 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BW006240018 | 10.130.0.6 | SANPADA RLY STN E ATM-2ABHISHEK CHS,SECTOR 30SANPADA WEST RLWY STATIONNavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-10 | - | - | Sagar | 2023-08-10 | - | By Hand | By Hand | By Hand | 653121 | 2120R502304260080 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
13 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NW006240014 | 10.130.0.10 | SBOA SCHOOL NERUL ATM-2SBOA PUBLIC SCHOOL,AYYAPPA RD,DR D Y PATIL VIDYANAGAR,SBOA PUBLIC SCHOOLNavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-14 | - | - | Kishan | 2023-08-10 | - | By Hand | By Hand | By Hand | 653105 | 2120R502304260063 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
14 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1NG006240081 | 10.130.0.14 | SECTOR 21 NERULDOCTOR HOUSE, SECTOR 21,DOCTOR HOUSENavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-14 | - | - | Kishan | 2023-08-10 | - | By Hand | By Hand | By Hand | 653123 | 2120R502304260113 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
15 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BB006240040 | 10.130.0.18 | JNPT ISBI JNPT ATMSBI JNPT ATMNavin ShevaUran | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-14 | - | - | Prashad | 2023-08-10 | - | By Hand | By Hand | By Hand | 653120 | 2120R502304260064 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
16 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BG006240020 | 10.130.0.22 | PANVELSBI KHANDA COLONY ATMSBI KHANDA COLONY ATMPanvel (M Cl)Panvel | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-11 | - | - | Kishan | 2023-08-10 | - | By Hand | By Hand | By Hand | 653125 | 2120R502304260078 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
17 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BW006240101 | 10.130.0.26 | URANNAGAON URAN SBI ATMNAGAON URAN SBI ATM Nagaon Uran | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-14 | - | - | Prashad | 2023-08-10 | - | By Hand | By Hand | By Hand | 653122 | 2120R502304260125 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
18 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BB006240136 | 10.130.0.30 | KAMOTHE SECTOR 20106, SION PANVEL EXPY, SECTOR 20,AISHWARYA AUTO STATIONKamothePanvel | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-11 | - | - | Kishan | 2023-08-10 | - | By Hand | By Hand | By Hand | 653118 | 2120R502304260085 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
19 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BH006240019 | 10.130.0.34 | PANVELSBI KHANDA COLONY ATMSBI KHANDA COLONY ATMPanvel (M Cl)Panvel | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-11 | - | - | Kishan | 2023-08-10 | - | By Hand | By Hand | By Hand | 653119 | 2120R502304260159 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
20 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BW006240038 | 10.130.0.38 | OPP. APNA BAZAR VASHISECTOR 1, VASHIOPP APNA BAZAARNavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-10 | - | - | Sagar | 2023-08-10 | - | By Hand | By Hand | By Hand | 653124 | 2120R502304260103 | Done | Sandeep Prajapati | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
21 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249018 | 10.130.0.74 | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-21 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653135 | 2120R502304260099 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
22 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249019 | 10.130.0.82 | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-21 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653142 | 2120R502304260174 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
29 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB001162005 | 10.130.1.50 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | Installed & Live | 2023-08-23 | - | - | Jitendra C - 9325359264 | 2023-08-21 | - | Delivery.com | 12364010164850 | Delivered | 653156 | 2120R502304260180 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
30 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB001162006 | 10.130.1.54 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | Installed & Live | 2023-08-23 | - | - | Jitendra C - 9325359264 | 2023-08-21 | - | Delivery.com | 12364010164850 | Delivered | 653157 | 2120R502304260172 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
25 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249021 | 10.130.0.54 | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-18 | - | - | Amol Vairat - 8999571090 | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653136 | 2120R502304260098 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
26 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249052 | 10.130.0.62 | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-18 | - | - | Amol Vairat - 8999571090 | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653148 | 2120R502304260179 | Done | Ashish Dubey | 2023-08-08 | DONE | Return | 2023-09-28 | Ajeet | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
27 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG000349014 | #N/A | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Jakindra P | machine under shifting | NA | - | - | Yogesh - 9021001191 | 2023-08-19 | - | Trackon | 500340025565 | Delivered | 653172 | 2120R502304260136 | Done | Ashish Dubey | 2023-08-08 | DONE | Return | 2023-09-28 | Ajeet | machine under shifting |  | NA | NA
28 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG000349015 | 10.130.1.126 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Jakindra P | Installed & Live | 2023-08-22 | - | - | Yogesh - 9021001191 / Parmeshwar Chavan 97303 26942 / Vishal 8805736615 | 2023-08-19 | - | Trackon | 500340025565 | Delivered | 653173 | 2120R502304260133 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
46 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB001162008 | 10.130.1.42 | GANDHI CHOWK, NEAR HANUMAN MANDIR, NAVAPUR -425418, DIST. DHULE | Dhule | Maharashtra | Mahendra M | Installed & Live | 2023-08-24 | - | - | Jitendra C - 9325359264 | 2023-08-21 | - | Delivery.com | 12364010164850 | Delivered | 653159 | 2120R502304260119 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
53 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000435019 | 10.130.1.46 | LAL BAHADUR SHASTRI MARKET, NANDURBAR - 425412 | NANDURBAR | Maharashtra | Mahendra M | Installed & Live | 2023-08-23 | - | - | Jitendra C - 9325359264 | 2023-08-21 | - | Delivery.com | 12364010164850 | Delivered | 653160 | 2120R502304260084 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
54 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB001162007 | 10.130.1.58 | MAIN ROAD, OPP. SBI, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | Installed & Live | 2023-08-23 | - | - | Jitendra C - 9325359264 | 2023-08-21 | - | Delivery.com | 12364010164850 | Delivered | 653158 | 2120R502304260166 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
69 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NH000441014 | 10.130.1.78 | SARDAR VALLABH PATEL ROAD, JALGAON -424201 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-25 | - | - | Jitendra C - 9325359264 | 2023-08-23 | - | Delivery.com | 12364010164850 | Delivered | 653197 | 2120R502304260173 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
70 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000272002 | 10.130.1.82 | SATOD ROAD, TEHSIL- YAVAL, DIST. JALGAON PN - 425301 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-22 | - | - | Jitendra C - 9325359264 | 2023-08-22 | - | Delivery.com | 12364010164850 | Delivered | 655176 | 2120R502304260154 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
31 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG006757001 | 10.130.1.158 | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | Chandrapur | Maharashtra | Ravikant D | Installed & Live | 2023-08-22 | - | - | Rahul Mishra- 9561689228 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653163 | 2120R502304260096 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
35 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S10A007249002 | 10.130.0.86 | ADITYA CORNER, TARABAI PARK, KOLHAPUR PIN 416003 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-22 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653150 | 2120R502304260163 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
32 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG006757002 | 10.130.1.166 | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | Chandrapur | Maharashtra | Ravikant D | Installed & Live | 2023-08-22 | - | - | Rahul Mishra- 9561689228 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653167 | 2120R502304260123 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
37 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BH001469107 | #N/A | ATM OWNER REQUESTED TO VACATE ATM LOBBY.NEW LOCATION STILL NOT FINALISED. | NA | Maharashtra | NA | Held Up | NA | - | - | - | - | - | Delivery.com | Pending to Dispatch | Delivered | 653200 | 2120R502304260109 | Done | Ashish Dubey | 2023-08-08 | DONE | Return | 2023-09-28 | Ajeet | Held Up |  | NA | NA
36 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NW004711003 | #N/A | ATM IS INRESTRICTED AREA OF ORDINANCE FACTORY, BHADRAWATI | BHADRAWATI | Maharashtra | Ravikant D | network issue at site | NA | - | - | Ravi D - 7710016117 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653169 | 2120R502304260081 | Done | Ashish Dubey | 2023-08-08 |  |  |  |  | network issue at site |  | NA | NA
38 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG003078002 | 10.130.1.154 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | Ravikant D | Installed & Live | 2023-08-22 | - | - | Rahul Mishra- 9561689228 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653164 | 2120R502304260074 | Done | Ashish Dubey | 2023-08-08 | DONE | Return | 2023-09-28 | Ajeet | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
40 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG007249064 | 10.130.0.42 | BPC PETROLINK A/P KUMBHOJ TALUKA HATKALANGALE DISTRICT KOLHAPUR PIN 41611 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-23 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-19 | - | Trackon | 2366579209 | Delivered | 653137 | 2120R502304260135 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
41 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NH000363003 | 10.130.1.90 | BPCL PETROL PUMP, NEAR SBI, DHARANGAON, DIST. JALGAON - 425105 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-21 | - | - | Jitendra C - 9325359264 | 2023-08-19 | - | Delivery.com | 12364010164850 | Delivered | 653198 | 2120R502304260120 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
39 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG011420001 | 10.130.1.178 | BHIWAPUR,INFRONT OF SBI BHIWAPUR BRANCH, TAH. UMRED DEIS- NAGPUR | Nagpur | Maharashtra | Ravikant D | Installed & Live | 2023-08-24 | - | - | Ravi D - 7710016117 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653171 | 2120R502304260161 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
43 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG001415002 | #N/A | CAD PULGAON MILITARY CAMP, PULGAON | Wardha | Maharashtra | Ravikant D | Kept on hold by BM due to renovation work | NA | - | - | Vendor | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653166 | 2120R502304260168 | Done | Ashish Dubey | 2023-08-08 |  |  |  |  | Kept on hold by BM due to renovation work |  | NA | NA
48 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB006757004 | 10.130.1.174 | GUJJAR COMPLEX NEAR SHIVAJI CHOWK, GADCHANDUR | Chandrapur | Maharashtra | Ravikant D | Installed & Live | 2023-08-22 | - | - | Rahul Mishra- 9561689228 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653170 | 2120R502304260141 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
45 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249057 | 10.130.0.98 | CPR HOSPITAL CAMPUS, KOLHAPUR 416002 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-19 | - | - | Amol Vairat - 8999571090 | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653145 | 2120R502304260121 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
57 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NB000501001 | 10.130.1.146 | NEAR ANANDVAN CHOWK, WARORA | Chandrapur | Maharashtra | Ravikant D | Installed & Live | 2023-08-23 | - | - | Ravi D - 7710016117 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653162 | 2120R502304260164 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
47 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249026 | 10.130.0.66 | GHODAVAT GROUP FACTORY, SANGLI ROAD, JAYSINGHPUR-416101 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-24 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-21 | - | Delivery.com | 12364010164846 | Delivered | 653147 | 2120R502304260165 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
58 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG004711002 | 10.130.1.162 | NEAR BHADRAWATI ORDINANCE FACTORY MAIN GATE, BHADRAWATI | BHADRAWATI | Maharashtra | Ravikant D | Installed & Live | 2023-08-25 | - | - | Ravi D - 7710016117 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653168 | 2120R502304260105 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
66 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000298007 | 10.130.1.150 | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | GADCHIROLLI | Maharashtra | Ravikant D | Installed & Live | 2023-08-24 | - | - | Ravi D - 7710016117 | 2023-08-21 | - | Delivery.com | 12364010164861 | Delivered | 653165 | 2120R502304260108 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
50 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S10F000393006 | 10.130.1.86 | JAMNER ROAD, NERI, DIST. JALGAON, PIN - 424104 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-21 | - | - | Jitendra C - 9325359264 | 2023-08-19 | - | Delivery.com | 12364010164850 | Delivered | 653177 | 2120R502304260143 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
51 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BH007249023 | 10.130.0.46 | KORGAONKAR PETROL PUMP, SANGLI PHATA, SHIROLI, DIST. KOLHAPUR-416122 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-22 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653139 | 2120R502304260167 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
52 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249059 | 10.130.0.90 | KRISHNA PETROLEUM, BPCL, TAKALA AREA, KOLHAPUR-416008 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-22 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-17 | - | Delivery.com | 12364010164846 | Delivered | 653140 | 2120R502304260151 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
33 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000527005 | 10.130.0.102 | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI -415311 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-24 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-19 | - | Delivery.com | 12364010164846 | Delivered | 653144 | 2120R502304260156 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
34 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000527006 | 10.130.0.114 | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI -415311 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-24 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-19 | - | Delivery.com | 12364010164846 | Delivered | 653153 | 2120R502304260171 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
55 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NH001207004 | 10.130.1.94 | MARWADI LANE, ERANDOL, DIST. JALGAON , ERANDOL -425109 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-21 | - | - | Jitendra C - 9325359264 | 2023-08-19 | - | Delivery.com | 12364010164850 | Delivered | 653199 | 2120R502304260144 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
56 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000325008 | 10.130.0.126 | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR PIN 413411 | Solapur | Maharashtra | Ishwar | Installed & Live | 2023-08-23 | - | - | Hamid - 9503707672 | 2023-08-24 | - | Trackon | 500340025574 | Delivered | 653143 | 2120R502304260145 | Done | Ashish Dubey | 2023-08-08 | DONE | Done |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
42 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S10G001372001 | 10.130.0.106 | C/O SHRI RAMCHANDRA PANDURANG RAUT, A/P PATAN, LIBRARY CHOWK, PATAN, DIST. SATARA. PIN 415206 | SATARA | Maharashtra | Shankar G | Installed & Live | 2023-08-25 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-21 | - | Delivery.com | 12364010164846 | Delivered | 653155 | 2120R502304260169 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
59 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000527007 | 10.130.0.110 | NEAR GANAPATI TEMPLE, GURUWAR PETH, A/P. TASGAON, DIST. SANGLI-416312 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-25 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-19 | - | Delivery.com | 12364010164846 | Delivered | 653154 | 2120R502304260147 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
62 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NW000471067 | 10.130.0.94 | OPPOSITE VASANTDADA SAKHAR KARKHANA, MADHAVNAGAR ROAD, SANGLI 416416 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-24 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-19 | - | Delivery.com | 12364010164846 | Delivered | 653146 | 2120R502304260110 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
60 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NW000325009 | 10.130.0.122 | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR 413411. | Solapur | Maharashtra | Ishwar | Installed & Live | 2023-08-28 | - | - | Hamid - 9503707672 | 2023-08-24 | - | Trackon | 500340025574 | Delivered | 653151 | 2120R502304260148 | Done | Ashish Dubey | 2023-08-08 | DONE | Done |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
61 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000335013 | 10.130.1.62 | OPP. SANTOSHI MATA HALL, BHUSAWAL - 425201, DIST. JALGAON | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-18 | - | - | Jitendra C - 9325359264 | 2023-08-18 | - | Delivery.com | 12364010164850 | Delivered | 653193 | 2120R502304260158 | Done | Ashish Dubey | 2023-08-08 | DONE | Return | 2023-09-28 | Ajeet | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
23 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BH000311003 | 10.130.1.106 | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati 444601 | Amravati | Maharashtra | Utkarsh G | Installed & Live | 2023-08-25 | - | - | Utkarsh G-9923441558 | 2023-08-22 | - | Trackon | 500340025547 | Delivered | 653192 | 2120R502304260075 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
63 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NG000335012 | 10.130.1.70 | PANCHMUKHI MANDIR, JALGAON ROAD, BHUSAWAL - 425201, DIST. NASHIK | Nashik | Maharashtra | Jitendra C | Installed & Live | 2023-08-18 | - | - | Jitendra C - 9325359264 | 2023-08-18 | - | Trackon | 2366579200 | Delivered | 653195 | 2120R502304260092 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
64 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249144 | 10.130.0.58 | POLICE PETROL PUMP, BAVADA ROAD, OPP. NANA NANI PARK, TARABAI PARK, KOLHAPUR 416002 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-22 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-18 | - | Delivery.com | 12364010164846 | Delivered | 653149 | 2120R502304260134 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
24 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BH000311010 | 10.130.1.118 | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati 444601 | Amravati | Maharashtra | Utkarsh G | Installed & Live | 2023-08-25 | - | - | Utkarsh G-9923441558 | 2023-08-22 | - | Trackon | 500340025547 | Delivered | 653178 | 2120R502304260073 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
44 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NC000311013 | 10.130.1.114 | Chandur Rly Road, near Wadali Garden, Amravati 444602 | Amravati | Maharashtra | Utkarsh G | Installed & Live | 2023-08-29 | - | - | Utkarsh G-9923441558 | 2023-08-22 | - | Trackon | 500340025547 | Delivered | 653179 | 2120R502304260091 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
67 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NH000407003 | 10.130.1.130 | Railway Station Campus, Main Road, Khamgaon, Dist. Buldhana 444303 | Buldhana | Maharashtra | Jakindra P | Installed & Live | 2023-08-23 | - | - | Yogesh - 9021001191 | 2023-08-19 | - | Trackon | 500340025565 | Delivered | 653174 | 2120R502304260157 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
68 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG007249053 | 10.130.0.70 | RATNA PETROLEUM, NEW WASHI NAKA, RADHANAGARI ROAD, KOLHAPUR-416002 | Kolhapur | Maharashtra | Shankar G | Installed & Live | 2023-08-21 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-17 | - | Delivery.com | 12364010164846 | Delivered | 653132 | 2120R502304260089 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
49 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BH000311005 | 10.130.1.102 | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati 444606 | Amravati | Maharashtra | Utkarsh G | Installed & Live | 2023-08-29 | - | - | Utkarsh G-9923441558 | 2023-08-23 | - | Trackon | 500340025547 | Delivered | 653191 | 2120R502304260162 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
65 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | S1BG003866048 | SBI | S1BH000311008 | 10.130.1.110 | Prof. Ram Meghe Square, Anjangaon Bari Road, Badnera 444701 | Amravati | Maharashtra | Utkarsh G | Installed & Live | 2023-08-30 | - | - | Utkarsh G-9923441558 | 2023-08-23 | - | Trackon | 500340025547 | Delivered | 653180 | 2120R502304260069 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
71 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG000335030 | 10.130.1.66 | SBI BHUSAWAL MAIN BRANCH, BHUSAWAL - 425201, DIST. JALGAON | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-18 | - | - | Jitendra C - 9325359264 | 2023-08-18 | - | Delivery.com | 12364010164850 | Delivered | 653194 | 2120R502304260142 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
72 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BG000471063 | 10.130.0.50 | SP OFFICE, SANGLI, VISHRAMBAG, SANGLI, 416416 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-24 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-21 | - | Delivery.com | 12364010164846 | Delivered | 653134 | 2120R502304260101 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
73 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NH002176002 | 10.130.1.134 | SSGMCE, SBI Colony, Shegaon, Dist Buldhana 444203 | Buldhana | Maharashtra | Jakindra P | Installed & Live | 2023-08-23 | - | - | Yogesh - 9021001191 | 2023-08-19 | - | Trackon | 500340025565 | Delivered | 653175 | 2120R502304260170 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
74 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BW000483058 | 10.130.0.118 | Survey no 110/1b , Sant Tukaram nagar, Vijapur Road, Solapur. 413004. | Solapur | Maharashtra | Ishwar | Installed & Live | 2023-08-21 | - | - | Hamid - 9503707672 | 2023-08-21 | - | Trackon | 500340025574 | Delivered | 653152 | 2120R502304260112 | Done | Ashish Dubey | 2023-08-08 | DONE | Done |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
75 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1BB001252002 | 10.130.1.138 | WCL COLONY WAGHODA, SAONER | Nagpur | Maharashtra | Ravikant D | Installed & Live | 2023-08-18 | - | - | Ravi D - 7710016117 | 2023-08-18 | - | Delivery.com | 12364010164861 | Delivered | 653161 | 2120R502304260070 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
76 | AdvantageSB | 2023-08-08 | Sudhir S | - | Router | - | - | SBI | S1NW000471068 | 10.130.0.78 | ZULELAL CHOWK, NEAR S T STAND SANGLI 416416 | Sangli | Maharashtra | Shankar G | Installed & Live | 2023-08-23 | - | - | Amol Vairat - 8999571090(Vendor) | 2023-08-21 | - | Delivery.com | 12364010164846 | Delivered | 653138 | 2120R502304260140 | Done | Ashish Dubey | 2023-08-08 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
| AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW003667003 | 10.130.0.198 | NEAR PEDHA HANUMAN TEMPLE PARBHANI | PARABHANI | Maharashtra | Kishore B | Installed & Live | 2023-09-30 | - | - | Kishore 97677 11023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_05 | 2120R502304260094 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
78 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NB003667026 | 10.130.0.210 | NEAR PEDHA HANUMAN TEMPLE PARBHANI | PARABHANI | Maharashtra | Kishore B | Installed & Live | 2023-09-30 | - | - | Kishore 97677 11023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_12 | 2120R502304260102 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
79 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020029006 | ip Not Found | NEAR SHIVAJI CHOWK AMBAJOGAI TAL AMBAJOGAI DIST BEED | Beed | Maharashtra | Jakindra P | No Network | NA | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_03 | 2120R502304260061 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | No Network |  | NA | NA
80 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BG020029001 | 10.130.0.250 | NEAR SHIVAJI CHOWK AMBAJOGAI TAL AMBAJOGAI DIST BEED | Beed | Maharashtra | Jakindra P | Installed & Live | 2023-08-29 | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_08 | 2120R502304260066 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
81 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020027002 | NOT Installed | BEED NAGAR ROAD NEAR COLLECTOR OFFICE BEED | Beed | Maharashtra | Hamid | Planned today but OEM denied | NA | - |  | Hamid | - | - | overseasairfreight | 500340025898 | Delivered | ADV_21 | 2120R502304260090 | Done | Received in WH | 2023-08-16 |  |  |  |  | Planned today but OEM denied |  | NA | NA
82 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S10G011151001 | 10.130.0.222 | CRPF CAMPUS NANDED MUDKHED ROAD TAL MUDKHED DIST NANDED | NANDED | Maharashtra | Kishore B | Installed & Live | 2023-08-25 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_24 | 2120R502304260065 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
83 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NH000282008 | NOT Installed | DAMBE BUILDING,TALERE BAZAAR, BELOW NEW FLY OVER, TALERE, MAHARASHTRA 416801 | SINDHUDURG | Maharashtra | Anil S | Network issue at site | NA | - | - | Anil Shinde- 9637704878 | - | - | overseasairfreight | 17255810043234 | Delivered | 653185 | 2120R502304260130 | Done | Received in WH | 2023-08-16 |  |  |  |  | Network issue at site |  | NA | NA
84 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NH020023005 | #N/A | DOCTORS LANE GANGAKHED NEAR AMBEDKAR STATUE POLICE STATION GANGAKHED DIST PARABHANI | PARABHANI | Maharashtra | Kishore B | OEM was ready but our team will attend on Monday | NA | - | - | Vishal- 7721977207 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_04 | 2120R502304260122 | Done | Received in WH | 2023-08-16 |  |  |  |  | OEM was ready but our team will attend on Monday |  | NA | NA
85 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW000282007 | 10.130.0.142 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | SINDHUDURG | Maharashtra | Anil S | Installed & Live | 2023-08-29 | - | - | Anil Shinde- 9637704878 | - | - | overseasairfreight | 17255810043234 | Delivered | 653184 | 2120R502304260155 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
86 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BG008851009 | 10.130.0.130 | GOA MEDICAL COLLEGE, BAMBOLIM, TISWADI GOA - 403202 | North Goa | Goa | Harendra S | Installed & Live | 2023-08-25 | - | - | Harendra Singh - 7385818988 | - | - | overseasairfreight | 500340025871 | Delivered | 653181 | 2120R502304260150 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
87 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BC000495001 | 10.130.0.154 | HOTEL LAUKIK BLDG, BAZARPETH ROAD, VENGURLA, SINDHUDURG, MAHARASHTRA- 416516 | SINDHUDURG | Maharashtra | Anil S | Installed & Live | 2023-08-28 | - | - | Anil Shinde- 9637704878 | - | - | overseasairfreight | 17255810043234 | Delivered | 653187 | 2120R502304260175 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
88 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020037010 | 10.130.0.238 | INSIDE GOVERNMENT MEDICAL COLLEGE LATUR | Latur | Maharashtra | Kunal K | Installed & Live | 2023-08-28 | - | - | Abhay- 9665157126 | - | - | overseasairfreight | 500340025880 | Delivered | ADV_23 | 2120R502304260178 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
89 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020049029 | 10.130.0.214 | INSIDE HUZUR SAHIB NANDED RAILWAY STATION PREMICES , NANDED RAILWATY STATION TAL DIST NANDED | NANDED | Maharashtra | Kishore B | Installed & Live | 2023-08-25 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_16 | 2120R502304260129 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
90 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020049028 | 10.130.0.226 | INSIDE SGGS COLLEGE PREMICES VISHNUPURI NANDED | NANDED | Maharashtra | Kishore B | Installed & Live | 2023-08-25 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_01 | 2120R502304260177 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
91 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020039015 | 10.130.1.6 | JANTRE COMPLEX DHOKI ROAD KALAMB DIST OSMANABAD | OSMANABAD | Maharashtra | Ishwar | Installed & Live | 2023-08-29 | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025880 | Delivered | ADV_18 | 2120R502304260104 | Done | Received in WH | 2023-08-16 | DONE | Done |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
92 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW011158001 | #N/A | LANJA, RATNAGIRI - 416701 | RATNAGIRI | Maharashtra | Anil S | material not received | NA | - | - | Vendor | - | - | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage |  |  |  |  | material not received |  | NA | NA
93 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NH020047001 | 10.130.1.14 | MAIN ROAD PARANDA DIST OSMANABAD | OSMANABAD | Maharashtra | Ishwar | Installed & Live | 2023-08-28 | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025880 | Delivered | ADV_19 | 2120R502304260100 | Done | Received in WH | 2023-08-16 | DONE | Done |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
94 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW020029003 | 10.130.0.242 | MONDHA ROAD TAL AMBAJOGAI DIST BEED | Beed | Maharashtra | Jakindra P | Installed & Live | 2023-08-29 | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_09 | 2120R502304260062 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
95 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG009905003 | 10.130.0.250 | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | PARABHANI | Maharashtra | Kishore B | Installed & Live | 2023-08-28 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_02 | 2120R502304260115 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
96 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BW017554145 | 10.130.0.178 | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | Jakindra P | Installed & Live | 2023-08-29 | - | - | Yogesh - 9021001191 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_07 | 2120R502304260086 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
97 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BW017554056 | 10.130.0.182 | NEAR MORESHWAR IOCL PETROL PUMP SHAHAGUNJ AURANGABAD | Aurangabad | Maharashtra | Jakindra P | Installed & Live | 2023-08-28 | - | - | Yogesh - 9021001191 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_26 | 2120R502304260152 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
98 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW020024001 | 10.130.0.202 | NEAR OLD POLICE STATION TAL HINGOLI | HINGOLI | Maharashtra | Santosh Gawai | Installed & Live | 2023-08-29 | - | - | Santosh Sir 90113 80867 / 9763552375 Kalamanuri | - | - | Pending to Dispatch | Delivered | Delivered | ADV_15 | 2120R502304260072 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
99 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG003667028 | 10.130.0.190 | NEAR RAILWAY STATION PARABHANI | PARABHANI | Maharashtra | Kishore B | Installed & Live | 2023-08-28 | - | - | Vishal- 7721977207 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_27 | 2120R502304260106 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
100 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG006039007 | #N/A | NEAR RAJESHWARI GENERAL STORES SHIVAJI CHOWK UDGIR TAL UDGIR DIST LATUR | Latur | Maharashtra | Kunal K | Planned today but OEM denied | NA | - | - | Abhay- 9665157126 | - | - | overseasairfreight | 500340025880 | Delivered | ADV_13 | 2120R502304260137 | Done | Received in WH | 2023-08-16 |  |  |  |  | Planned today but OEM denied |  | NA | NA
101 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW017554067 | 10.130.0.186 | NEAR SHENDRABAN PUMP SHAHAGUNJ AURANGABAD | Aurangabad | Maharashtra | Jakindra P | Installed & Live | 2023-08-28 | - | - | Yogesh - 9021001191 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_11 | 2120R502304260117 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
102 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG003670003 | 10.130.1.10 | NEAR SHIVAJI CHOWK NILANGA TAL NILANGA DIST LATUR | Latur | Maharashtra | Kunal K | Installed & Live | 2023-08-29 | - | 9503707672 | Abhay- 9665157126 | - | - | overseasairfreight | 500340025880 | Delivered | ADV_22 | 2120R502304260082 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
103 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW020962001 | 10.130.0.254 | NEAR SRT MEDICAL COLLEGE AMBAJOGAI | Beed | Maharashtra | Jakindra P | Installed & Live | 2023-08-29 | - | - | Hamid Pathan - 9503707672 | - | - | overseasairfreight | 500340025898 | Delivered | ADV_06 | 2120R502304260124 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
104 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BG008851006 | 10.130.0.138 | NEAR TREASURY PANAJI BRANCH. | North Goa | Goa | Harendra S | Installed & Live | 2023-08-24 | - | - | Harendra Singh - 7385818988 | - | - | overseasairfreight | 500340025871 | Delivered | 653183 | 2120R502304260068 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
105 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BG000471064 | #N/A | OPPOSITE MARKET YARD, MIRAJ ROAD, SANGLI, DIST SANGLI-416446 | Sangli | Maharashtra | Shankar G | material not received | NA | - | - | Amol Vairat - 8999571090(Vendor) | - | - | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage | Material not received from Advantage |  |  |  | material not received |  | NA | NA
106 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S10A000393004 | 10.130.1.74 | RAILWAY STATION, JALGAON- 425002 | Jalgaon | Maharashtra | Mahendra M | Installed & Live | 2023-08-29 | - | - | Jitendra C - 9325359264 | - | - | overseasairfreight | 2366579353 | Delivered | 653196 | 2120R502304260128 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | NCR | 27ES/2023/01657 | 2023-10-31
107 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020056001 | 10.130.0.230 | SHIVAJI CHOWK NEAR STATE BANK OF INDIA KANDHAR TAL KANDHAR DIST NANDED | NANDED | Maharashtra | Kishore B | Installed & Live | 2023-08-30 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_17 | 2120R502304260127 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | CMS(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
108 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NW008851057 | NOT Installed | SHRIDHAR APARTMENT COOP HSG SOC., SHOP NO 3, MERCES, NEAR MERCES GRAM PANCHAYAT, ILHAS GOA 403005 | North Goa | Goa | Harendra S | OEM schedule still not received | NA | - | - | Harendra Singh - 7385818988 | - | - | overseasairfreight | 500340025871 | Delivered | 653182 | 2120R502304260067 | Done | Received in WH | 2023-08-16 |  |  |  |  | OEM schedule still not received |  | NA | NA
109 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1NG020049018 | 10.130.0.218 | ZILLA PARISHAD MAIN BUILDING OPP SHIVAJI MAHARAJ STATUE RAILWAY STATION ROAD NANDED | NANDED | Maharashtra | Kishore B | Installed & Live | 2023-08-24 | - | - | Kishore Bahadure- 9767711023 | - | - | overseasairfreight | 17942710003010 | Delivered | ADV_25 | 2120R502304260083 | Done | Received in WH | 2023-08-16 | DONE |  |  |  | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
110 | AdvantageSB | 2023-08-05 | Sudhir S | - | Router | - | - | SBI | S1BW006240024 | 10.130.0.2 | VASHI RAILWAY STATIONVASHI RAILWAY STATION, NAVI MUMBAIVASHI RAILWAY STATIONNavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-08-05 | - | - | Sagar | 2023-08-05 | - | By Hand | By Hand | Delivered | - | 2120R502304260146 | Handover Directly to Engineer by Advantage Team | Handover Directly to Engineer by Advantage Team | 2023-08-05 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
111 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | ONSITE | - | SBI | S10B007339003 | 10.130.1.34 | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-28 | - | - | Nana - 7875777801 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653116 | 2120R502304260131 | Done | DONE | [5 empty] | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
112 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | ONSITE | - | SBI | S1BB007339004 | 10.130.1.22 | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Pune | Maharashtra | Kailash R | Installed & Live | 2023-08-28 | - | - | Nana - 7875777801 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653116 | 2120R502304260097 | Done | DONE | [5 empty] | HITACHI(MS20) | DIEBOLD | 27ES/2023/01657 | 2023-10-31
113 | AdvantageSB | 2023-07-27 | Sudhir S | - | Router | - | - | SBI | S1BW021332001 | 10.130.0.246 | Ambajogai- Ahmedpur road, Ghatnandur,431519 | Beed | Maharashtra | Jakindra P | Installed & Live | 2023-08-29 | - | - | Hamid Pathan - 9503707672 | 2023-08-21 | - | By Bus | By Bus | Delivered | 653116 | 2120R502304260061 | Done | Jakindra P |  | DONE |  |  |  | CMS(MS20) | HYOSUNG | 27ES/2023/01657 | 2023-10-31
114 | AdvantageSB | 2023-09-28 | Sudhir S | - | Router | - | - | SBI | SIBW000454561 | #N/A | SARANG SOC. SAHAKAR NAGAR PUNE | Pune | Maharashtra | Kailash R | Kept on hold by BM due to renovation work | NA | - | - | Kishore 97677 11023 | 2023-08-21 | - | - | - | - | - | - | Done | Kailash R | [5 empty] | Kept on hold by BM due to renovation work |  | NA | NA
115 | AdvantageSB | 2023-10-23 | Sudhir S | - | Router | - | - | SBI | S1BG000300173 | 10.130.5.250 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Ashish J | Installed & Live | 2023-11-10 | - | - | Ashish Jain |  | - | By Bus | By Bus | Delivered | ADV 50 | 2120R502309010127 | Done | Ashish J | [5 empty] | CMS(MS20) | DIEBOLD |  | 2023-11-29
116 | AdvantageSB | 2024-01-16 | Sudhir S | - | Router | offsite | - | SBI | S1NW015417161 | 10.130.10.246 | Amber Fort ,Jaipur 302028 | Jaipur | Rajashthan | Pradhan meena | Installed & Live | 2024-01-17 | - | - | Akaram Khan |  | - | Trackon | 500384556188 | Delivered | ADV 50 | 2120R502309180357 | Done | Akaram Khan | 2024-01-17 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | Pending | Pending
117 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1BW032090129 | 10.130.10.70 | BPCL PETROL PUMP , SIRSI ROAD Chitrakoot Jaipur | Jaipur | Rajashthan | Pradhan meena | Installed & Live | 2024-01-29 | - | - | Akaram Khan |  | - | Trackon | 500384556188 | Delivered | ADV 50 | 2120R502309180355 | Done | Akaram Khan | 2024-01-17 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | Pending | Pending
118 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1NW015415465 | 10.130.11.6 | Shanti Auto mobile Petrol Pump , Banar Road jodhpur RAIKA BAGH JODHPUR | Jaipur | Rajashthan | Pradhan meena | Installed & Live | 2024-02-02 | - | - | Akaram Khan |  | - | Trackon | 2371597346 | Delivered | ADV 50 | 2120R502309180291 | Done | Akaram Khan | 2024-01-17 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | Pending | Pending
119 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1BB031252062 | 10.130.10.210 | SBI MOBILE ATM VAN, KOTA | Jaipur | Rajashthan | Pradhan meena | Installed & Live | 2024-02-02 | - | - | Akaram Khan |  | - | Trackon | 2371597345 | Delivered | ADV 50 | 2120R502309180214 | Done | Akaram Khan | 2024-01-17 | DONE |  |  |  | HITACHI(MS20) | HYOSUNG | Pending | Pending
120 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1BB031162015 | 10.130.10.178 | SBI MOBILE ATM VAN, BIKANER | Jaipur | Rajashthan | Pradhan meena | Installed & Live | 2024-02-02 | - | - | Dharamraj |  | - | Trackon | 2371597348 | Delivered | ADV 50 | 2120R502309180180 | Done | Dharamraj | 2024-01-17 | DONE
121 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1NW006094058 | 10.130.10.238 | ARYA NAGAR ALWAR POLICE LINE,ALWAR | ALWAR | Rajashthan | Pradhan meena | Installed & Live | 2024-02-06 | - | - | Ashish Sharma |  | - | Trackon | 2371597347 | Delivered | ADV 50 | 2120R502309180209 | Done | Ashish Sharma | 2024-01-17 | DONE
122 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1NB015415039 | 10.130.10.174 | SBI MOBILE ATM VAN, JALORI GATE, JODHPUR | JODHPUR | Rajashthan | Pradhan meena | Installed & Live | 2024-02-03 | - | - | vinod kumar sharma |  | - | Trackon | 2371597346 | Delivered | ADV 50 | 2120R502309180212 | Done | vinod kumar sharma | 2024-01-17 | DONE
123 | AdvantageSB | 2024-01-22 | Sudhir S | - | Router | offsite | - | SBI | S1BB031104029 | 10.130.10.58 | SBI MOBILE ATM VAN, AJMER | Ajmer | Rajashthan | Pradhan meena | Installed & Live | 2024-02-08 | - | - | Navin Choudhary |  | - | Trackon | 500384556170 | Delivered | ADV 50 | 2120R502309180160 | Done | Navin Choudhary | 2024-01-17 | DONE
124 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NW006335001 | 10.130.10.62 | COLLECTORATE PREMISE, BHILWARA, RAJASTHAN,311001 | BHILWARA | Rajashthan | Pradhan meena | Installed & Live | 2024-02-17 | - | - | Prakash |  | - | Trackon | 500384556170 | Delivered | ADV 50 | 2120R502309180361 | Done | Prakash | 2024-01-17 | DONE
125 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NG006335023 | 10.130.10.206 | COLLECTORATE PREMISE, BHILWARA, RAJASTHAN,311001 | BHILWARA | Rajashthan | Pradhan meena | Installed & Live | 2024-02-17 | - | - | Prakash |  | - | Trackon | 500384556170 | Delivered | ADV 50 | 2120R502309180158 | Done | Prakash | 2024-01-17 | DONE
126 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NG031036003 | 10.130.10.242 | RAILWAY STATION DAUSA LALSOT ROAD DAUSA | Dausa | Rajashthan | Pradhan meena | Installed & Live | 2024-02-17 | - | - | Rakesh |  | - | Trackon | 500384556188 | Delivered | ADV 50 | 2120R502309180203 | Done | Rakesh | 2024-01-17 | DONE
127 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NG031036004 | 10.130.10.74 | INFRONT OF DOTHA DAUSA | Dausa | Rajashthan | Pradhan meena | Installed & Live | 2024-02-21 | - | - | Rakesh |  | - | Trackon | 500384556188 | Delivered | ADV 50 | 2120R502309180256 | Done | Rakesh | 2024-01-17 | DONE
128 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1BB032090102 | 10.130.10.250 | SBI ATM Amber Towe Sansar Chand Road Jaipur | Amber Tower | Rajashthan | Pradhan meena | WIP OEM Confirmation Awaited (Our Router LIVE on 22-02-2024) | 2024-02-22 | - | - | Rakesh |  | - | Trackon | 500384556188 | Delivered | ADV 50 | 2120R502309180216 | Done | Rakesh | 2024-01-17 | DONE
129 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NG002424007 | 10.130.10.54 | MES GATE MOUNT ABU DISTT SIROHI | MOUNT ABU | Rajashthan | Pradhan meena | Installed & Live | 2024-02-29 | - | - | Rakesh |  | - | Trackon |  | Delivered | ADV 50 | 2120R502309180114 | Done | Pradhan meena | 2024-01-17
130 | AdvantageSB | 2024-02-10 | Sudhir S | - | Router | offsite | - | SBI | S1NW002424001 | NA | AIRFORCE MOUNT ABU | MOUNT ABU | Rajashthan | Pradhan meena | Router with Engg Mr. Harkesh ATM machine Lan Cable has been cut by a rat; after the problem is fixed, please confirm with us so that we may start the installation. | 2024-02-29 | - | - | Rakesh |  | - | Trackon |  |  | ADV 50 |  | Done | Pradhan meena | 2024-01-17

## Esclation (hidden)
CTS Esclation Matrix for Quick Response.
CTS Esclation Matrix for Quick Response.
Level | Role | Contact Detail | Email ID
L-1 | Team Lead | Sandeep Prajapati - 8976768954 | sandeepprajapati@comforttechno.com
L-2 | Sr. Manager | Anant Sawant – 7738467458 | asawant@cssindia.in
L-3 | MD | Ashish Dubey -9967200000 | ashish@comforttechno.com
CTS NOC Shift Esclation Matrix for Quick Response
1 | NOC | Amrapali Mogale - 91374 84652 | NA
2 | NOC | Sourav Gupta - 9569227458 | NA

## LHO (hidden)
Nodal Officer MAH
NAME | AO | NUMBER | Mail ID | FLM Name | NUMBER | Mail ID |  |  |  | Sr.No | MSP | Name | Mail ID | Number | Mail
SRIKANT MYNEKAR | AO KOLHAPUR | 7875559621 | s.mynekar@sbi.co.in | [6 empty] | L-1 | Hitachi | Helpdesk | hd-sbi-cluster2@hitachi-payments.com | 07947489862/08045810966 | TO | Sunil kumar Mishra 9150012379
SANGITA AZAGAONKAR | AO PANAJI | 7030945043 | sangita.azgaonkar@sbi.co.in | [9 empty] | hd-sbi-cluster1@hitachi-payments.com |  | TO
GANESH BHANDARI | AO PUNE | 7588234592 | ganesh.bhandari@sbi.co.in | [9 empty] | sbi.kolkata@hitachi-payments.com |  | TO
VINAY RAUT | AO AURANGABAD | 9975046181 | vinaykumar.raut@sbi.co.in | Bhagwan kasare | 9158383897 | NA | [6 empty] | raju.kahar@hitachi-payments.com |  | TO
BALASAHEB SHINDE | AO NANDED | 8975533197 | balasaheb.shinde@sbi.co.in | [9 empty] | suvidha.m@hitachi-payments.com |  | TO
PRADIP UMARE | AO NASIK | 7391098730 | mgrac.aonashik@sbi.co.in | [7 empty] | SLM | Anshuman | anshuman.pawar@hitachi-payments.com | 9150079468 | CC
RAMESHWAR KALKAR | AO AMRAVATI | 9766901555 | rameshwar.kalkar@sbi.co.in | [7 empty] | AHM | Makrand | makarand.ramane@hitachi-payments.com | 9150020577 | CC
HARPREET KAUR | AO NAGPUR | 7722036344 | Cmatm2 Lhomah <cmac2.mah@sbi.co.in> | [7 empty] | KOL | Sumit Hande | sumit.hande@hitachi-payments.com | 9150079467 | CC
Rupali Dhuri | Nashik | 9769390171 | mgrac.aonashik@sbi.co.in | [7 empty] | BANK | Vaibhav P. Nagare | vaibhav.nagare@hitachi-payments.com | 9150012377 | CC
Shrikrishna | Jalgaon | 9850823086 | shrikrishna.karandikar@sbi.co.in | [11 empty] | CC
AGM 1 | LHO |  | AGMATM1 LHOMAH' <agmac1.mah@sbi.co.in | [6 empty] | L-3 | Team Leader | Yogesh Betakar | Yogesh.Batekar@hitachi-payments.com | 7358798582 | CC
AGM2 | LHO |  | 'agmsnp mah' <agmsnp.mah@sbi.co.in> | [8 empty] | Vishal Keny | vishal.keny@hitachi-payments.com | 9150020578 | CC
Common mail to ATC | LHO |  | Cmatm2 Lhomah <cmac2.mah@sbi.co.in> | [6 empty] | L-4 | Assist. Manager | Sunil kumar Mishra | sunil.mishra@hitachi-payments.com | 9150012379 | CC
|  |  | ac3.ccc@sbi.co.in | [8 empty] | Devendra Bambulkar | Devendra.Bambulkar@hitachi-payments.com | 9150012380 | CC
[12 empty] | Sachin Devkar | sachin.devkar@hitachi-payments.com | 9150030690 | CC
LHO MUMBAI |  |  |  | Sr.No | MSP | Name | Mail ID | Number | Mail | L-5 | Sr. Manager | Ajit Nirbhavane | ajit.nirbhavane@hitachi-payments.com | 7305059475 | CC
Name | Mail id | Mob No |  | 1 | Hitachi | Ajit Nirbhavane | ajit.nirbhavane@hitachi-payments.com | 7305059475 | To | L-6 | Deputy Vice President | Bipin Chaubey | bipin.chaubey@hitachi-payments.com | 9015435167 | CC
Common mail (Mum) | CMATM LHOMUM <cmatm.lhomum@sbi.co.in> |  |  | 2 | Hitachi | Sachin.Devkar | Sachin.Devkar@hitachi-payments.com | 9150030690 | CC | [5 empty] | CC
Bhagwat Behera AGM 1 | 'AGM ATM LHO MUMBAI' <agmac1.mum@sbi.co.in> |  |  | 3 | Hitachi | Bipin.chaubey | bipin.chaubey@hitachi-payments.com |  | CC
Umesh Prasad AGM2 | agmac2.mum@sbi.co.in |  |  | 4 | Hitachi | Devendra M. Bambulkar | Devendra.Bambulkar@hitachi-payments.com |  | CC
Arun Meena (CM) | Navi Mumbai | 9871002023 |  | 5 | CMS | Yogesh More | more.yogesh@cms.com | 9136790561 | To
|  |  |  | 6 | CMS | Ritesh Chavana | 'ritesh.chavan@cms.com' | 9004040323 | To
|  |  |  | 7 | SBI | Rajesh | ac3.ccc@sbi.co.in |  | CC
|  |  |  | 8 | SBI | Hemendra Swaroop | hemendra.swaroop@sbi.co.in |  | CC
|  |  |  | 9 | SBI | Hemendra Swaroop | 'agmac.ops@sbi.co.in' |  | CC

## Sheet2 (hidden)
SIM Cards manufacturer | NEW SIM CARD NUMBER | Mobile No | Bank | ATMID | ATMID 2 | Site Type | Address | City | State | SIM Cards manufacturer | OLD SIM CARD NUMBER / Mobile No | Amount | Engginer Name | Visit Date | Status | Final remark | Fund Status
BSNL | 899166291410650000 | 7588045416 | SBI | S1NW000282007 | - | OFFSITE | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | SINDHUDURG | Maharashtra | AIRTEL | 8991922305937404457U / '8655432647 | 350 | Anil Shinde | 2023-10-03 | Sim card Replace | Visit Done | Pending
- | - | - | SBI | S1BB006240136 | - | OFFSITE | KAMOTHE SECTOR 20106, SION PANVEL EXPY, SECTOR 20,AISHWARYA AUTO STATIONKamothePanvel | Mumbai | Maharashtra | - | - | - | Kissan | 2023-09-30 | UPS battery | Visit Done | Pending
- | - | - | SBI | S1BG008851006 | - | OFFSITE | NEAR TREASURY PANAJI BRANCH. | North Goa | Goa | - | - | - | Harendra | 2023-10-02 | UPS battery | Visit Done | Pending
- | - | - | SBI | S1NG000325008 | - | OFFSITE | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR PIN 413411 | Solapur | Maharashtra | - | - | - | Ishwar | 2023-10-04 | Area Power failure | NA | NA
- | - | - | SBI | S1NW000325009 | - | OFFSITE | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR 413411. | Solapur | Maharashtra | - | - | - | Ishwar | 2023-10-04 | Area Power failure | NA | NA
- | - | - | SBI | S1BH000311005 | - | OFFSITE | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati 444606 | Amravati | Maharashtra | - | - | 250 | Utkarsh | 2023-10-04 | New Adopter Install | Visit Done | Pending
- | - | - | SBI | S1BB001252002 | - | OFFSITE | WCL COLONY WAGHODA, SAONER | Nagpur | Maharashtra | - | - | - | Ravi Dubey | 2023-10-05 | Area Power failure | NA | NA
- | - | - | SBI | S1BG008851006 | - | OFFSITE | NEAR TREASURY PANAJI BRANCH. | North Goa | Goa | - | - | - | Harendra | 2023-10-05 | Van Welding Working | NA | NA
- | - | - | SBI | Materials | - | Materials | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | Mumbai | Maharashtra | - | - | 455 | Rishab | 2023-10-06 | Advantage To Sion Warehouse Materials (50 Router with full Set) | Visit Done | Pending
- | - | - | SBI | S1BW017554145 | - | OFFSITE | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | - | - | 200 | Yogesh Patil | 2023-10-08 | Shutter Lock | Visit Done | Upload In Portal
- | - | - | SBI | S1NG006240081 | - | OFFSITE | SECTOR 21 NERULDOCTOR HOUSE, SECTOR 21,DOCTOR HOUSENavi Mumbai (M Corp.)Thane | Mumbai | Maharashtra | - | - | - | Ravi guard | 2023-10-11 | Visit Atm Machine | Visit Done | Pending
- | - | - | SBI | Materials | - | Materials | Sion jain Society Warehouse to Ghansholi MIDC Advantage OFFICE | Mumbai | Maharashtra | - | - | 480 | Sandeep | 2023-10-12 | Sion Warehouse To Advantage Materials (50 Router with full Set) | Visit Done | Pending
- | - | - | SBI | S1BH007249023 | - | OFFSITE | KORGAONKAR PETROL PUMP, SANGLI PHATA, SHIROLI, DIST. KOLHAPUR-416122 | Kolhapur | Maharashtra | - | - | NA | Shankar gadkar | 2023-10-12 | Visit Done | Visit Done | Pending
- | - | - | SBI | S1NW000282007 | - | OFFSITE | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | SINDHUDURG | Maharashtra | - | - | 350 | Anil Shinde | 2023-10-13 | Visit Done | Visit Done | Pending
- | - | - | SBI | S1BW017554145 | - | OFFSITE | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | - | - | - | Yogesh Patil | 2023-10-13 | Not Viisted | NA | NA
- | - | - | SBI | S1BG000410001 | - | OFFSITE | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | Pune | Maharashtra | - | - | 350 | Kiran | 2023-10-13 | Visit Done | Visit Done | Pending
- | - | - | SBI | S1NG000298007 | - | OFFSITE | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | GADCHIROLLI | Maharashtra | - | - | 1200 | Ravi Dubey | 2023-10-13 | Visit Done | Visit Done | Pending
- | - | - | SBI | S1BG001415002 | - | OFFSITE | CAD PULGAON MILITARY CAMP, PULGAON | Wardha | Maharashtra |  | - | NA | Ravi Dubey | 2023-10-14 | Router move from Pune To Nagapur | Visit Done | Pending
- | - | - | SBI | S1BW017554145 | - | OFFSITE | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | - | - | 250 | Yogesh Patil | 2023-10-16 | Visit Done | Visit Done | Pending
- | - | - | SBI | S1BW017554145 | - | OFFSITE | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | - | - | 250 | Yogesh Patil | 2023-10-17 | Yogesh Visit Done Configuration Done By Navnath | Visit Done | Pending
- | - | - | SBI | S1BW017554145 | - | OFFSITE | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | Maharashtra | - | - | 250 | Yogesh Patil | 2023-10-21 | Yogesh Visit Done Configuration Done By Navnath | Visit Done | Pending
- | - | - | SBI | S1BG003078002 | - | OFFSITE | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | - | - | 300 | Ravikant D | 2023-10-27 | Sanjay Visit at Site Antenna installation Done | Visit Done | Pending
- | - | - | SBI | S1BG003078002 | - | OFFSITE | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | JIO | 89918640400775694222 / 9209561751 | 750 | Ravikant D | 2023-11-03 | 3PIN Adopter installation / New JIO SIM Card for feasibility Check | Visit Done | Pending

## Recocalation (hidden)
Materials Received By Advantage
Sr No | ATMID | Address | City | State | CSS BM | Sr. NO | Remark | Router Faulty | Handover date | Handover Person | POD Details | Sr No | MSP | Bank | ATMID | IP | Address | City | State | CSS BM | Materials BOQ / Serial Number | Qnt | Dispatch Address | Tickeck ID | Material Disptached Date | Courier Detail | Docket Detail | Delivery Status | Delivery Date | Installation Status | Date of Installation
1 | S1NG020027002 | BEED NAGAR ROAD NEAR COLLECTOR OFFICE BEED | Beed | Maharashtra | Hamid | 2120R502304260090 | 1Qnts 4G Router (ADV 50) Serial No :- 2120R502304260090 | Return | 2024-01-23 | Ajeet | DTDC (P67575921) | 1 | AdvantageSB | SBI | S1NW000282007 | 10.130.0.142 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | SINDHUDURG | Maharashtra | Anil S | 8991922305937404457U / '8655432647 (BSNL SIM CARD) | 1 | Locally Purchase | NA | 2023-10-03 | Locally Purchase | Locally Purchase | Locally Purchase | 2023-10-03 | Completed | 2023-10-03
2 | S1NH000282008 | DAMBE BUILDING,TALERE BAZAAR, BELOW NEW FLY OVER, TALERE, MAHARASHTRA 416801 | SINDHUDURG | Maharashtra | Anil S | 2120R502304260130 | 1Qnts 4G Router (ADV 50) Serial No :- 2120R502304260130 | Return | 2024-01-23 | Ajeet | Shree Anjani Courier ('1725520895) | 2 | AdvantageSB | SBI | S1BH000311005 | 10.130.1.102 | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati 444606 | Amravati | Maharashtra | Utkarsh G | New Adopter Install | 1 | Locally Purchase | NA | 2023-10-04 | Locally Purchase | Locally Purchase | Locally Purchase | 2023-10-04 | Completed | 2023-10-04
3 | S1NW008851057 | SHRIDHAR APARTMENT COOP HSG SOC., SHOP NO 3, MERCES, NEAR MERCES GRAM PANCHAYAT, ILHAS GOA 403005 | North Goa | Goa | Harendra S | 2120R502304260067 | 1Qnts 4G Router (ADV 50) Serial No :- 2120R502304260067 | Return | 2024-01-23 | Ajeet | Shree Nandan courier ('23026100053818) | 3 | AdvantageSB | SBI | Materials | - | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | Mumbai | Maharashtra | Ashish J | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | 50 | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | NA | 2023-10-06 | BY Hand | BY Hand | Delivered | 2023-10-12 | Completed | 2023-10-12
4 | S1BG007249052 | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | Kolhapur | Maharashtra | Shankar G | 2120R502304260179 | AdV50 4G Router | Return | 2023-09-28 | Ajeet | BY Bus | 4 | AdvantageSB | SBI | S1BG003078002 | 10.130.1.154 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | Ravikant D | Big 4G Antenna (10 meter wire) | 2 | Clear Secured Service Pvt Ltd Sanjay nandanwar (7710016143 / 8551892771) Bhagat Singh chouk, junona road near shiv mandir Chandrapur 442403. | NA | 2023-10-19 | DTDC | V88954793 | Delivered | 2023-10-25 | Completed | 2023-10-25
5 | S1BG000349014 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Jakindra P | 2120R502304260136 | AdV50 4G Router | Return | 2023-09-28 | Ajeet | BY Bus | 5 | AdvantageSB | SBI | S1BG003078002 | 10.130.1.154 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | Ravikant D | 3 Pin_12 v Adopter | 1 | Clear Secured Service Pvt Ltd Sanjay nandanwar (7710016143 / 8551892771) Bhagat Singh chouk, junona road near shiv mandir Chandrapur 442403. | O202310300621 | 2023-10-30 | DTDC | V88954793 | Delivered | 2023-10-30 | Completed | 2023-10-30
6 | S1BH001469107 | ATM OWNER REQUESTED TO VACATE ATM LOBBY.NEW LOCATION STILL NOT FINALISED. |  | Maharashtra | NA | 2120R502304260109 | AdV50 4G Router | Return | 2023-09-28 | Ajeet | BY Bus | 6 | AdvantageSB | SBI | S1BG000410001 | 10.130.0.174 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | Pune | Maharashtra | Kailash R | AdV50 4G Router (2120R502304260064) | 1 | Dispatch by Navnath by BUS | NA | 2023-11-05 | By Bus | By Bus | Delivered | 2023-11-05 | Completed | 2023-11-06
7 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | Ravikant D | 2120R502304260074 | AdV50 4G Router | Return | 2023-09-28 | Ajeet | BY Bus | 6 | AdvantageSB | SBI | S1BG000300173 | 10.130.5.250 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Ashish J | AdV50 4G Router /3 Pin_12 v Adopter / 5mtr Antenna / Big GPS Antenna | 1 | Sandeep Prajapati / Comfort Techno Services Pvt. Ltd /Sharm -Siddhi Vinayak Co-Op Premises Society Ltd J1-A Wing ,A-120 First Floor Wadala Truck Terminal, Mumbai, Maharashtra 400037 Mob: +91 8976768954. | New Installation colaba | 2023-11-08 | BY hand | By Hand | Delivered | 2023-11-08 | Completed | 2023-11-08
8 | S1NG000335013 | OPP. SANTOSHI MATA HALL, BHUSAWAL - 425201, DIST. JALGAON | Jalgaon | Maharashtra | Mahendra M | 2120R502304260158 | AdV50 4G Router | Return | 2023-09-28 | Ajeet | BY Bus | 7 | AdvantageSB | SBI | S1BG000300173 | 10.130.5.250 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Ashish J | JIO SIM Cards (9324164086 – 89918740400313597118) | 1 | Sandeep Prajapati / Comfort Techno Services Pvt. Ltd /Sharm -Siddhi Vinayak Co-Op Premises Society Ltd J1-A Wing ,A-120 First Floor Wadala Truck Terminal, Mumbai, Maharashtra 400037 Mob: +91 8976768954. | New Installation colaba | 2023-11-14 | BY hand | By Hand | Delivered | 2023-11-14 | Completed | 2023-11-14
9 | Materials | Sion Warehouse To Advantage Materials (50 Router with full Set) | Mumbai | Maharashtra | Ashsish jain | Sion Warehouse To Advantage Materials (50 Router with full Set) | Sion Warehouse To Advantage Materials (50 Router with full Set) | Return | 2023-10-12 | Ajeet | BY OLA | 8 | AdvantageSB | SBI | S1BB001252002 | 10.130.1.138 | WCL COLONY WAGHODA, SAONER | Nagpur | Maharashtra | Ravikant D | Big 4G Antenna (10 meter wire) | 2 | C/O Chandra Prakash Dubey 91584 34514 / 7710016117 Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | N202311200949 | 2023-11-22 | DTDC | D78428931 | Delivered | 2023-11-25 | Completed | 2023-11-29
9 | S1NG000298007 | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | GADCHIROLLI | Maharashtra | Ravikant D | 2120R502304260108 | AdV50 4G Router | Return | 2023-11-16 | Ajeet | DTDC (M34028424) | 8 | AdvantageSB | SBI | S1NB001162005 | 10.130.1.50 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | AdV50 4G Router (2120R502309180237) | 1 | DTDC NANDURBAR new , G. T. P. COLLEGE ROAD, SHANI MANRIRA JAAWAL, OPPOSITE R. K. TRANSPORT, NANDURBAR, MAHARASHTRA Pin-425412 | N202311231048 | 2023-11-23 | DTDC | D77068457 | Delivered | 2023-11-27 | Completed | 2023-11-28
10 | SIBW000454561 | SARANG SOC. SAHAKAR NAGAR PUNE | Pune | Maharashtra | Kailash R | NA | 2Qnt Anteena / GPS Antenna / 2 pin Adpotor | Return | 2023-12-11 | Ajeet | Roshan Hand over Router to Navnath | 9 | AdvantageSB | SBI | S1NB001162005 | 10.130.1.50 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | 3 Pin_12 v Adopter | 1 | DTDC NANDURBAR new , G. T. P. COLLEGE ROAD, SHANI MANRIRA JAAWAL, OPPOSITE R. K. TRANSPORT, NANDURBAR, MAHARASHTRA Pin-425412 | N202311231048 | 2023-11-23 | DTDC | D77068457 | Delivered | 2023-11-27 | Completed | 2023-11-28
11 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | Pune | Maharashtra | Kailash R | 2120R502304260093 | AdV50 4G Router | Return | 2023-11-16 | Ajeet | Roshan Hand over Router to Navnath | 10 | AdvantageSB | SBI | S1NW020024001 | 10.130.1.202 | NEAR OLD POLICE STATION TAL HINGOLI | HINGOLI | Maharashtra | Santosh Gawai | AdV50 4G Router (2120R502309180165) | 1 | संतोष गवई (7020545399 /9011380867 ) लेडी हार्डिंग समोर चिखली रोड वाशिम पिन :- 444505 | N202311231046 | 2023-11-23 | DTDC | V88966647 | Delivered | 2023-11-28 | Completed | 2023-11-29
12 | S1NW000282007 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | SINDHUDURG | Maharashtra | Anil Shinde | NA | Sim card Replace & 2Qnt Anteena | Return | 2023-11-08 | Ajeet |  | 11 | AdvantageSB | SBI | S1NW020024001 | 10.130.1.202 | NEAR OLD POLICE STATION TAL HINGOLI | HINGOLI | Maharashtra | Santosh Gawai | 3 Pin_12 v Adopter | 1 | संतोष गवई (7020545399 /9011380867 ) लेडी हार्डिंग समोर चिखली रोड वाशिम पिन :- 444505 | N202311231046 | 2023-11-23 | DTDC | V88966647 | Delivered | 2023-11-28 | Completed | 2023-11-29
13 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Chandrapur | Maharashtra | Ravikant D | NA | 2Qnt 4G Antenna (3 meter wire) / 2 Pin_12 v Adopter | Return | 2023-12-19 | Navnath | M28947024 | 12 | AdvantageSB | SBI | S1NB000501001 | 10.130.1.146 | NEAR ANANDVAN CHOWK, WARORA | Chandrapur | Maharashtra | Ravikant D | AdV50 4G Router / 3 Pin_12 v Adopter (2120R502309180817) | 1 | C/O Chandra Prakash Dubey 91584 34514 / 7710016117 Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | N202311231074 | 2023-11-23 | By Bus | 244 | Delivered | 2023-11-25 | Completed | 2023-11-25
14 | S1BG000300173 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Asish Jain | 9167468244 – 8991027390101102585 | Vodafone SIM Card (9167468244 – 8991027390101102585) | Return | 2023-11-17 | Ajeet |  | 13 | AdvantageSB | SBI | S1NB000501001 | 10.130.1.146 | NEAR ANANDVAN CHOWK, WARORA | Chandrapur | Maharashtra | Ravikant D | 3 Pin_12 v Adopter | 1 | C/O Chandra Prakash Dubey 91584 34514 / 7710016117 Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | N202311231074 | 2023-11-23 | By Bus | 244 | Delivered | 2023-11-25 | Completed | 2023-11-25
15 | S1NB000501001 | NEAR ANANDVAN CHOWK, WARORA | Chandrapur | Maharashtra | Ravikant D | 2120R502304260164 | AdV50 4G Router / 2 Pin_12 v Adopter | Return | 2023-12-12 | Ajeet | BY Bus LR 2599 | 14 | AdvantageSB | SBI | S1BG000349015 | 10.130.1.126 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Jakindra P | AdV50 4G Router (2120R502309180195) | 1 | Yogesh Patil (9021001191) Rider Store Shop no 4 Mayanger Below Shgrila hotel Executive n2 Cidco Aurangabad Pincode :- 431001. | N202311241103 | 2023-11-23 | By Bus | 245 | Delivered | 2023-11-26 | Completed | 2023-11-27
16 | S1BG000349015 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Yogesh Patil | 2120R502304260133 | AdV50 4G Router / 2 Pin_12 v Adopter | Pending | Missing | Missing | Missing | 15 | AdvantageSB | SBI | S1BG000349015 | 10.130.1.126 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | Maharashtra | Jakindra P | 3 Pin_12 v Adopter | 1 | Yogesh Patil (9021001191) Rider Store Shop no 4 Mayanger Below Shgrila hotel Executive n2 Cidco Aurangabad Pincode :- 431001. | N202311241103 | 2023-11-23 | By Bus | 245 | Delivered | 2023-11-26 | Completed | 2023-11-27
17 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | Maharashtra | Mahendra M | 2120R502304260180 | AdV50 4G Router / 2 Pin_12 v Adopter | Return | 2023-12-11 | Ajeet | Shree Maruti (23094100004789) | 16 | AdvantageSB | SBI | S1BG000300173 | 10.130.5.250 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Ashish J | VI SIM Cards (9167605870 – 8991027390101102589) | 1 | Sandeep Prajapati / Comfort Techno Services Pvt. Ltd /Sharm -Siddhi Vinayak Co-Op Premises Society Ltd J1-A Wing ,A-120 First Floor Wadala Truck Terminal, Mumbai, Maharashtra 400037 Mob: +91 8976768954. | New Installation colaba | 2023-12-06 | BY hand | By Hand | Delivered | 2023-12-06 | Completed | 2023-12-07
18 | S1NW020024001 | NEAR OLD POLICE STATION TAL HINGOLI | HINGOLI | Maharashtra | Santosh Gawai | 2120R502304260072 | AdV50 4G Router / 2 Pin_12 v Adopter | Return | 2023-12-13 | 150 | WSM98589 | 17 | AdvantageSB | SBI | S1NG009905003 | 10.130.0.250 | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | Mumbai | Maharashtra | Kishore | Big 4G Antenna (10 meter wire) | 2 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | D202312141629 | 2023-12-14 | DTDC | D78794526 | Delivered | 2023-12-16 | Materials With Kishore (pending to Install)
20 | S1BG000300173 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | Mumbai | Maharashtra | Asish Jain | VI SIM Cards (9167605870 – 8991027390101102589) | Vodafone SIM Card (9167468244 – 8991027390101102585) | Return | 2023-12-11 | Ajeet | By Hand | 18 | AdvantageSB | SBI | S1NG009905003 | 10.130.0.250 | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | Mumbai | Maharashtra | Kishore | SIM CARD (JIO) | 1 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 |  | 2024-01-09
21 | S1BB001252002 | WCL COLONY WAGHODA, SAONER | Nagpur | Maharashtra | Ravikant D | NA | 2Qnt 4G Antenna (3 meter wire) | Return | 2023-12-12 | Ajeet | BY Bus LR 2599
22 | S1NG009905003 | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | Mumbai | Maharashtra | Kishore | NA | 2Qnt 4G Antenna (3 meter wire) | Materials With Kishore (pending to Install)

## Sheet3 (hidden)
Sr. no. | New ATM I | TermId | ATM | ADDRESS 4 | Address | City | ms Vendor1 | ID on Make | Instatlled
1 |  | S1NG007249064 | 10.130.0.42 | AO KOLHAPUR | BPC PETROLINK A/P KUMBHOJ TALUKA HATKALANGALE DISTRICT KOLHAPUR PIN 41611 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
2 |  | S1BH007249023 | 10.130.0.46 | AO KOLHAPUR | KORGAONKAR PETROL PUMP, SANGLI PHATA, SHIROLI, DIST. KOLHAPUR-416122 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
3 |  | S1BG000471063 | 10.130.0.50 | AO KOLHAPUR | SP OFFICE, SANGLI, VISHRAMBAG, SANGLI, 416416 | Sangli | HITACHI(MS20) | DIEBOLD | Done
4 |  | S1BG007249021 | 10.130.0.54 | AO KOLHAPUR | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
5 |  | S1BG007249144 | 10.130.0.58 | AO KOLHAPUR | POLICE PETROL PUMP, BAVADA ROAD, OPP. NANA NANI PARK, TARABAI PARK, KOLHAPUR 416002 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
6 |  | S1BG007249052 | 10.130.0.62 | AO KOLHAPUR | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
7 |  | S1BG007249026 | 10.130.0.66 | AO KOLHAPUR | GHODAVAT GROUP FACTORY, SANGLI ROAD, JAYSINGHPUR-416101 | Sangli | HITACHI(MS20) | DIEBOLD | Done
8 |  | S1BG007249053 | 10.130.0.70 | AO KOLHAPUR | RATNA PETROLEUM, NEW WASHI NAKA, RADHANAGARI ROAD, KOLHAPUR-416002 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
9 |  | S1BG007249018 | 10.130.0.74 | AO KOLHAPUR | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
10 |  | S1NW000471068 | 10.130.0.78 | AO KOLHAPUR | ZULELAL CHOWK, NEAR S T STAND SANGLI 416416 | Sangli | HITACHI(MS20) | HYOSUNG | Done
11 |  | S1BG007249019 | 10.130.0.82 | AO KOLHAPUR | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
12 |  | S10A007249002 | 10.130.0.86 | AO KOLHAPUR | ADITYA CORNER, TARABAI PARK, KOLHAPUR PIN 416003 | Kolhapur | HITACHI(MS20) | NCR | Done
13 |  | S1BG007249059 | 10.130.0.90 | AO KOLHAPUR | KRISHNA PETROLEUM, BPCL, TAKALA AREA, KOLHAPUR-416008 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
14 |  | S1NW000471067 | 10.130.0.94 | AO KOLHAPUR | OPPOSITE VASANTDADA SAKHAR KARKHANA, MADHAVNAGAR ROAD, SANGLI 416416 | Sangli | HITACHI(MS20) | HYOSUNG | Done
15 |  | S1BG007249057 | 10.130.0.98 | AO KOLHAPUR | CPR HOSPITAL CAMPUS, KOLHAPUR 416002 | Kolhapur | HITACHI(MS20) | DIEBOLD | Done
16 |  | S1NG000527005 | 10.130.0.102 | AO KOLHAPUR | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI -415311 | Sangli | HITACHI(MS20) | DIEBOLD | Done
17 |  | S10G001372001 | 10.130.0.106 | AO KOLHAPUR | C/O SHRI RAMCHANDRA PANDURANG RAUT, A/P PATAN, LIBRARY CHOWK, PATAN, DIST. SATARA. PIN 415206 | Satara | CMS(MS20) | DIEBOLD | Done
18 |  | S1NG000527007 | 10.130.0.110 | AO KOLHAPUR | NEAR GANAPATI TEMPLE, GURUWAR PETH, A/P. TASGAON, DIST. SANGLI-416312 | Sangli | HITACHI(MS20) | DIEBOLD | Done
19 |  | S1NG000527006 | 10.130.0.114 | AO KOLHAPUR | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI -415311 | Sangli | HITACHI(MS20) | DIEBOLD | Done
20 |  | S1BW000483058 | 10.130.0.118 | AO KOLHAPUR | Survey no 110/1b , Sant Tukaram nagar, Vijapur Road, Solapur. 413004. | Solapur | HITACHI(MS20) | HYOSUNG | Done
21 |  | S1NW000325009 | 10.130.0.122 | AO KOLHAPUR | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR 413411. | Solapur | HITACHI(MS20) | HYOSUNG | Done
22 |  | S1NG000325008 | 10.130.0.126 | AO KOLHAPUR | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR PIN 413411 | Solapur | HITACHI(MS20) | DIEBOLD | Done
23 |  | S1BG008851009 | 10.130.0.130 | AO PANAJI | GOA MEDICAL COLLEGE, BAMBOLIM, TISWADI GOA - 403202 | Tiswadi | HITACHI(MS20) | DIEBOLD | Done
24 |  | S1BG008851006 | 10.130.0.138 | AO PANAJI | NEAR TREASURY PANAJI BRANCH. | Panaji | HITACHI(MS20) | DIEBOLD | Done
25 |  | S1NW000282007 | 10.130.0.142 | AO PANAJI | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | Malvan | HITACHI(MS20) | HYOSUNG | Done
26 |  | S1BC000495001 | 10.130.0.154 | AO PANAJI | HOTEL LAUKIK BLDG, BAZARPETH ROAD, VENGURLA, SINDHUDURG, MAHARASHTRA- 416516 | Sindhdurgh | HITACHI(MS20) | NCR | Done
27 |  | S1NG000454433 | 10.130.0.158 | AO PUNE | DR. SUJATA RAVAT, 42/1, SHANTA CLINIC & GYM, NEAR SHIVRAJ SCHOOL, GANESH NAGAR, PUNE | Pune | HITACHI(MS20) | DIEBOLD | Done
28 |  | S1NW000454187 | 10.130.0.162 | AO PUNE | SHOP NO.A/7, ARJUN PARK, KALE-PADAL ROAD, SASANENAGAR, PUNE 411028. LANDMARK: SBI SASANENAGAR BRANCH | Pune | HITACHI(MS20) | HYOSUNG | Done
29 |  | S1NG000555005 | 10.130.0.166 | AO PUNE | THE LONAWALA INDUSTRIAL ESTATE CO-OPERATIVE LTD. LONAWALA. 410401. LANDMARK: SBI IE LONAWALA BRANCH | Lonavala | HITACHI(MS20) | DIEBOLD | Done
30 |  | S1BB000410003 | 10.130.0.170 | AO PUNE | KRISHI UTPANN BAJAR SAMITI, CHHANTRAPATI SHIVAJI MARKET YARD, RAJGURUNAGAR (KHED), PUNE 410505. | Khed | HITACHI(MS20) | NCR | Done
31 |  | S1BG000410001 | 10.130.0.174 | AO PUNE | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | Bhimashankar | HITACHI(MS20) | DIEBOLD | Done
32 |  | S1BW017554145 | 10.130.0.178 | AO AURANGABAD | NEAR HOTEL KAILASH VERUL AURANGABAD | Aurangabad | HITACHI(MS20) | HYOSUNG | Done
33 |  | S1BW017554056 | 10.130.0.182 | AO AURANGABAD | NEAR MORESHWAR IOCL PETROL PUMP SHAHAGUNJ AURANGABAD | Aurangabad | HITACHI(MS20) | HYOSUNG | Done
34 |  | S1NW017554067 | 10.130.0.186 | AO AURANGABAD | NEAR SHENDRABAN PUMP SHAHAGUNJ AURANGABAD | Aurangabad | HITACHI(MS20) | HYOSUNG | Done
35 |  | S1NG003667028 | 10.130.0.190 | AO AURANGABAD | NEAR RAILWAY STATION PARABHANI | Parabhani | HITACHI(MS20) | DIEBOLD | Done
36 |  | S1NW003667003 | 10.130.0.198 | AO AURANGABAD | NEAR PEDHA HANUMAN TEMPLE PARBHANI | Parabhani | CMS(MS20) | HYOSUNG | Done
37 |  | S1NW020024001 | 10.130.0.202 | AO AURANGABAD | NEAR OLD POLICE STATION TAL HINGOLI | Hingoli | CMS(MS20) | HYOSUNG | Done
38 |  | S1NG009905003 | 10.130.0.206 | AO AURANGABAD | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | Sailu | CMS(MS20) | DIEBOLD | Done
39 |  | S1NB003667026 | 10.130.0.210 | AO AURANGABAD | NEAR PEDHA HANUMAN TEMPLE PARBHANI | Parabhani | CMS(MS20) | NCR | Done
40 |  | S1NG020049029 | 10.130.0.214 | AO NANDED | INSIDE HUZUR SAHIB NANDED RAILWAY STATION PREMICES , NANDED RAILWATY STATION TAL DIST NANDED | Nanded | HITACHI(MS20) | DIEBOLD | Done
41 |  | S1NG020049018 | 10.130.0.218 | AO NANDED | ZILLA PARISHAD MAIN BUILDING OPP SHIVAJI MAHARAJ STATUE RAILWAY STATION ROAD NANDED | Nanded | HITACHI(MS20) | DIEBOLD | Done
42 |  | S10G011151001 | 10.130.0.222 | AO NANDED | CRPF CAMPUS NANDED MUDKHED ROAD TAL MUDKHED DIST NANDED | Nanded | CMS(MS20) | DIEBOLD | Done
43 |  | S1NG020049028 | 10.130.0.226 | AO NANDED | INSIDE SGGS COLLEGE PREMICES VISHNUPURI NANDED | Nanded | HITACHI(MS20) | DIEBOLD | Done
44 |  | S1NG020056001 | 10.130.0.230 | AO NANDED | SHIVAJI CHOWK NEAR STATE BANK OF INDIA KANDHAR TAL KANDHAR DIST NANDED | Nanded | CMS(MS20) | DIEBOLD | Done
45 |  | S1NG020037010 | 10.130.0.238 | AO NANDED | INSIDE GOVERNMENT MEDICAL COLLEGE LATUR | Latur | HITACHI(MS20) | DIEBOLD | Done
46 |  | S1NW020029003 | 10.130.0.242 | AO NANDED | MONDHA ROAD TAL AMBAJOGAI DIST BEED | Beed | CMS(MS20) | HYOSUNG | Done
47 |  | S1BG020029001 | 10.130.0.250 | AO NANDED | NEAR SHIVAJI CHOWK AMBAJOGAI TAL AMBAJOGAI DIST BEED | Beed | CMS(MS20) | DIEBOLD | Done
48 |  | S1NW020962001 | 10.130.0.254 | AO NANDED | NEAR SRT MEDICAL COLLEGE AMBAJOGAI | Ambajoga | CMS(MS20) | HYOSUNG | Done
49 |  | S1NG020039015 | 10.130.1.6 | AO NANDED | JANTRE COMPLEX DHOKI ROAD KALAMB DIST OSMANABAD | Osmanabad | HITACHI(MS20) | DIEBOLD | Done
50 |  | S1NG003670003 | 10.130.1.10 | AO NANDED | NEAR SHIVAJI CHOWK NILANGA TAL NILANGA DIST LATUR | Latur | CMS(MS20) | DIEBOLD | Done
51 |  | S1NH020047001 | 10.130.1.14 | AO NANDED | MAIN ROAD PARANDA DIST OSMANABAD | Osmanabad | HITACHI(MS20) | DIEBOLD | Done
52 |  | S1BW001469101 | 10.130.1.18 | AO NASHIK | POOJA AVENUE, SHANTI PARK, UPNAGAR, NASHIK - 422006 | Nashik | HITACHI(MS20) | HYOSUNG | Done
53 |  | S1BH001469028 | 10.130.1.26 | AO NASHIK | 493/267, SATPUR GANGAPUR LINK ROAD , ASHOK NAGAR, NASHIK - 422012 | Nashik | HITACHI(MS20) | DIEBOLD | Done
54 |  | S1BA000440001 | 10.130.1.30 | AO NASHIK | YEOLA ROAD, AT POST - VINCHUR, DIST. NASHIK PIN - 422306 | Nashik | HITACHI(MS20) | NCR | Done
55 |  | S1NG005392007 | 10.130.1.38 | AO NASHIK | NEAR GANGADHAR TALKIES, AT POST SINNAR , DIST NASHIK, PIN - 422103 | Nashik | HITACHI(MS20) | DIEBOLD | Done
56 |  | S1NB001162008 | 10.130.1.42 | AO NASHIK | GANDHI CHOWK, NEAR HANUMAN MANDIR, NAVAPUR -425418, DIST. DHULE | Dhule | CMS(MS20) | NCR | Done
57 |  | S1NG000435019 | 10.130.1.46 | AO NASHIK | LAL BAHADUR SHASTRI MARKET, NANDURBAR - 425412 | Nandurbar | HITACHI(MS20) | DIEBOLD | Done
58 |  | S1NB001162005 | 10.130.1.50 | AO NASHIK | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | CMS(MS20) | NCR | Done
59 |  | S1NB001162006 | 10.130.1.54 | AO NASHIK | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | Dhule | CMS(MS20) | NCR | Done
60 |  | S1NB001162007 | 10.130.1.58 | AO NASHIK | MAIN ROAD, OPP. SBI, NAVAPUR - 425418 , DIST. DHULE | Dhule | CMS(MS20) | NCR | Done
61 |  | S1NG000335013 | 10.130.1.62 | AO NASHIK | OPP. SANTOSHI MATA HALL, BHUSAWAL - 425201, DIST. JALGAON | Jalgaon | HITACHI(MS20) | DIEBOLD | Done
62 |  | S1BG000335030 | 10.130.1.66 | AO NASHIK | SBI BHUSAWAL MAIN BRANCH, BHUSAWAL - 425201, DIST. JALGAON | Jalgaon | HITACHI(MS20) | DIEBOLD | Done
63 |  | S1NG000335012 | 10.130.1.70 | AO NASHIK | PANCHMUKHI MANDIR, JALGAON ROAD, BHUSAWAL - 425201, DIST. NASHIK | Nashik | HITACHI(MS20) | DIEBOLD | Done
64 |  | S10A000393004 | 10.130.1.74 | AO NASHIK | RAILWAY STATION, JALGAON- 425002 | Jalgaon | HITACHI(MS20) | NCR | Done
65 |  | S1NH000441014 | 10.130.1.78 | AO NASHIK | SARDAR VALLABH PATEL ROAD, JALGAON -424201 | Jalgaon | CMS(MS20) | DIEBOLD | Done
66 |  | S1NG000272002 | 10.130.1.82 | AO NASHIK | SATOD ROAD, TEHSIL- YAVAL, DIST. JALGAON PN - 425301 | Jalgaon | CMS(MS20) | DIEBOLD | Done
67 |  | S10F000393006 | 10.130.1.86 | AO NASHIK | JAMNER ROAD, NERI, DIST. JALGAON, PIN - 424104 | Jalgaon | HITACHI(MS20) | DIEBOLD | Done
68 |  | S1NH000363003 | 10.130.1.90 | AO NASHIK | BPCL PETROL PUMP, NEAR SBI, DHARANGAON, DIST. JALGAON - 425105 | Jalgaon | CMS(MS20) | DIEBOLD | Done
69 |  | S1NH001207004 | 10.130.1.94 | AO NASHIK | MARWADI LANE, ERANDOL, DIST. JALGAON , ERANDOL -425109 | Jalgaon | HITACHI(MS20) | DIEBOLD | Done
70 | S1BG003866050 | S1BH000311005 | 10.130.1.102 | AO AMRAVATI | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati 444606 | Amravati | CMS(MS20) | DIEBOLD | Done
71 | S1BG003866046 | S1BH000311003 | 10.130.1.106 | AO AMRAVATI | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati 444601 | Amravati | CMS(MS20) | DIEBOLD | Done
72 | S1BG003866048 | S1BH000311008 | 10.130.1.110 | AO AMRAVATI | Prof. Ram Meghe Square, Anjangaon Bari Road, Badnera 444701 | Amravati | CMS(MS20) | DIEBOLD | Done
73 | S1BB003866045 | S1NC000311013 | 10.130.1.114 | AO AMRAVATI | Chandur Rly Road, near Wadali Garden, Amravati 444602 | Amravati | CMS(MS20) | NCR | Done
74 | S1BG003866051 | S1BH000311010 | 10.130.1.118 | AO AMRAVATI | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati 444601 | Amravati | CMS(MS20) | DIEBOLD | Done
75 |  | S1BG000349015 | 10.130.1.126 | AO AMRAVATI | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | Buldhana | HITACHI(MS20) | DIEBOLD | Done
76 |  | S1NH000407003 | 10.130.1.130 | AO AMRAVATI | Railway Station Campus, Main Road, Khamgaon, Dist. Buldhana 444303 | Buldhana | HITACHI(MS20) | DIEBOLD | Done
77 |  | S1NH002176002 | 10.130.1.134 | AO AMRAVATI | SSGMCE, SBI Colony, Shegaon, Dist Buldhana 444203 | Buldhana | HITACHI(MS20) | DIEBOLD | Done
78 |  | S1BB001252002 | 10.130.1.138 | AO NAGPUR | WCL COLONY WAGHODA, SAONER | Nagpur | CMS(MS20) | NCR | Done
79 |  | S1NB000501001 | 10.130.1.146 | AO NAGPUR | NEAR ANANDVAN CHOWK, WARORA | Warora | CMS(MS20) | NCR | Done
80 |  | S1NG000298007 | 10.130.1.150 | AO NAGPUR | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | Gadchirolli | CMS(MS20) | DIEBOLD | Done
81 |  | S1BG003078002 | 10.130.1.154 | AO NAGPUR | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Nagpur | CMS(MS20) | DIEBOLD | Done
82 |  | S1BG006757001 | 10.130.1.158 | AO NAGPUR | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | Gadchandur | CMS(MS20) | DIEBOLD | Done
83 |  | S1BG004711002 | 10.130.1.162 | AO NAGPUR | NEAR BHADRAWATI ORDINANCE FACTORY MAIN GATE, BHADRAWATI | Bhadrawati | CMS(MS20) | DIEBOLD | Done
84 |  | S1BG006757002 | 10.130.1.166 | AO NAGPUR | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | Gadchandur | CMS(MS20) | DIEBOLD | Done
85 |  | S1NB006757004 | 10.130.1.174 | AO NAGPUR | GUJJAR COMPLEX NEAR SHIVAJI CHOWK, GADCHANDUR | Gadchandur | CMS(MS20) | NCR | Done
86 |  | S1BG011420001 | 10.130.1.178 | AO NAGPUR | BHIWAPUR,INFRONT OF SBI BHIWAPUR BRANCH, TAH. UMRED DEIS- NAGPUR | Nagpur | CMS(MS20) | DIEBOLD | Done
87 |  | S1BW006240024 | 10.130.0.2 | AO MUMBAI | VASHI RAILWAY STATIONVASHI RAILWAY STATION, NAVI MUMBAIVASHI RAILWAY STATIONNavi Mumbai (M Corp.)Thane | Navi Mumbai | HITACHI(MS20) | HYOSUNG | Done
88 |  | S1BW006240018 | 10.130.0.6 | AO MUMBAI | SANPADA RLY STN E ATM-2ABHISHEK CHS,SECTOR 30SANPADA WEST RLWY STATIONNavi Mumbai (M Corp.)Thane | Navi Mumbai | HITACHI(MS20) | HYOSUNG | Done
89 |  | S1NW006240014 | 10.130.0.10 | AO MUMBAI | SBOA SCHOOL NERUL ATM-2SBOA PUBLIC SCHOOL,AYYAPPA RD,DR D Y PATIL VIDYANAGAR,SBOA PUBLIC SCHOOLNavi Mumbai (M Corp.)Thane | Navi Mumbai | HITACHI(MS20) | HYOSUNG | Done
90 |  | S1NG006240081 | 10.130.0.14 | AO MUMBAI | SECTOR 21 NERULDOCTOR HOUSE, SECTOR 21,DOCTOR HOUSENavi Mumbai (M Corp.)Thane | Navi Mumbai | HITACHI(MS20) | DIEBOLD | Done
91 |  | S1BB006240040 | 10.130.0.18 | AO MUMBAI | JNPT ISBI JNPT ATMSBI JNPT ATMNavin ShevaUran | Navi Mumbai | HITACHI(MS20) | NCR | Done
92 |  | S1BG006240020 | 10.130.0.22 | AO MUMBAI | PANVELSBI KHANDA COLONY ATMSBI KHANDA COLONY ATMPanvel (M Cl)Panvel | Navi Mumbai | HITACHI(MS20) | DIEBOLD | Done
93 |  | S1BW006240101 | 10.130.0.26 | AO MUMBAI | URANNAGAON URAN SBI ATMNAGAON URAN SBI ATMNagaonUran | Navi Mumbai | HITACHI(MS20) | HYOSUNG | Done
94 |  | S1BB006240136 | 10.130.0.30 | AO MUMBAI | KAMOTHE SECTOR 20106, SION PANVEL EXPY, SECTOR 20,AISHWARYA AUTO STATIONKamothePanvel | Navi Mumbai | HITACHI(MS20) | NCR | Done
95 |  | S1BH006240019 | 10.130.0.34 | AO MUMBAI | PANVELSBI KHANDA COLONY ATMSBI KHANDA COLONY ATMPanvel (M Cl)Panvel | Navi Mumbai | HITACHI(MS20) | DIEBOLD | Done
96 |  | S1BW006240038 | 10.130.0.38 | AO MUMBAI | OPP. APNA BAZAR VASHISECTOR 1, VASHIOPP APNA BAZAARNavi Mumbai (M Corp.)Thane | Navi Mumbai | HITACHI(MS20) | HYOSUNG | Done
97 | New ATM I | S10B007339003 | 10.130.1.34 | AO Pune | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Pune | HITACHI(MS20) | DIEBOLD | Done
98 | New ATM I | S1BB007339004 | 10.130.1.22 | AO Pune | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | Pune | HITACHI(MS20) | DIEBOLD | Done
99 | New ATM I | S1BW021332001 | 10.130.0.246 | AO NANDED | Ambajogai- Ahmedpur road, Ghatnandur,431519 | Beed | CMS(MS20) | HYOSUNG | Done
Th

## BOQ (hidden)
Sr No | Materials BOQ | Qnt | Sr No | Materials BOQ | Qnt
1 | AdV50 4G Router | 50 | 1 | AdV50 4G Router | 1
2 | 2 Pin_12 v Adopter | 50 | 2 | 2 Pin_12 v Adopter | 1
3 | Big 4G Antenna | 50 | 3 | Small 4G Antenna | 2
4 | Small 4G Antenna | 50 | 4 | GPS Antenna | 1
5 | BIG GPS Antenna | 50
Sr No | Materials BOQ | Qnt
1 | 2 Pin_12 v Adopter | 1
2 | Small 4G Antenna | 2
3 | GPS Antenna | 1
Sr No | Materials BOQ | Qnt | Sr No | Materials BOQ | Qnt
1 | AdV50 4G Router | 1 | 1 | AdV50 4G Router | 1
2 | 3 Pin_12 v Adopter | 1 | 2 | 3 Pin_12 v Adopter | 1
3 | GPS Antenna | 1 | 3 | GPS Antenna | 1
|  |  | 4 | 4G Antenna (5mtrs) | 2

## Fund (hidden)
Vertical | Sub Categories | BENEFICIARY NAME | BANK NAME | BENE ACCOUNT NUMBER | IFSC CODE | AMOUNT | Status | DISCRIPTION | CSS LOCAL BRANCH | STATE | SUP. NAME | CUSTOMER | BANK | ATM ID | MONTH | Remarks | Fund Transferred Status | Fund Transferred Date | Batch no | Address | Work Status
E-surveillance | Advantage SBI | yogesh pralhad rothe | STATE BANK OF INDIA | 39587291479 | SBIN0061267 | 200 | Service Call / ATM Machine | Service Call | Aurangabad | Maharashtra | Anant Sir | Advantage | SBI | S1BW017554145 | 2023-10-08 | Transportation charges - 200 | - | - | - | NEAR HOTEL KAILASH VERUL AURANGABAD | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 450 | Deliver | Transportation Mumbai To Sion | Chandrapur | Maharashtra | Sanjay S | Advantage | SBI | NA | 2023-10-01 | Transportation charges - 450 | - | - | - | NA | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 250 | Deliver | Transportation Chandarpur To Latur By BUS | Chandrapur | Maharashtra | Sanjay S | Advantage | SBI | S1NG020037010 | 2023-10-01 | Transportation charges - 250 | - | - | - | INSIDE GOVERNMENT MEDICAL COLLEGE LATUR | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 250 | Deliver | Transportation Chandarpur To Pune By BUS | Chandrapur | Maharashtra | Sanjay S | Advantage | SBI | S1BG001415002 | 2023-10-01 | Transportation charges - 250 | - | - | - | CAD PULGAON MILITARY CAMP, PULGAON | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 300 | 2 Antenna Installation | Antenna Installation | Chandrapur | Maharashtra | Sanjay S | Advantage | SBI | S1BG003078002 | 2023-10-01 | Transportation charges - 300 | - | - | - | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 350 | 3PIN Adopter installation | Router | Chandrapur | Maharashtra | Sanjay S | Advantage | SBI | S1BG003078002 | 2023-11-01 | Transportation charges - 300 | - | - | - | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240 | 600 | Service Call / ATM Machine | Transport Charge 120 km | Nagpur | Maharashtra | Ravi Dubey | Advantage | SBI | S1BB001252002 | 2023-11-01 | Transportation charges - 300 | - | - | - | WCL COLONY WAGHODA, SAONER | Done
E-surveillance | Advantage SBI | Ravikant Chandraprakash Dubey - 42669 | Bank Of Maharashtra | 20029381132 | MAHB0000240

## Servie Fund (hidden)
Visits with laptop & Courier charge
Sr no | ATM ID | Address | Repeated visits count | expenses per visit paid | Total expenses | Km two way
1 | S1BG007249018 | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | 5 | 200 | 1000 | 20 km
2 | S1NW000282007 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | 7 | 500 | 3500 | 200 km
3 | S1BB001252002 | WCL COLONY WAGHODA, SAONER | 4 | 450 | 1800 | 120 km
4 | S1BA000440001 | YEOLA ROAD, AT POST - VINCHUR, DIST. NASHIK PIN - 422306 | 3 | 500 | 1500 | 165 km
5 | S1NH000441014 | SARDAR VALLABH PATEL ROAD, JALGAON -424201 | 3 | 350 | 1050 | 130 km
6 | S1NG000527005 | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI -415311 | 3 | 1000 | 3000 | 240 km
7 | S1BG007249053 | RATNA PETROLEUM, NEW WASHI NAKA, RADHANAGARI ROAD, KOLHAPUR-416002 | 3 | 200 | 600 | local
8 | S10B007339003 | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune -411606 | 3 | 200 | 600 | local
9 | S1NG009905003 | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU. | 2 | 1200 | 2400 | 270 km
10 | S1NG000325008 | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR PIN 413411 | 2 | 500 | 1000 | 220 km
11 | S1NW000325009 | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR 413411. | 2 | 500 | 1000 | 160 km
12 | S1BG006757001 | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | 2 | 1500 | 3000 | 400 km
13 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR ( from Chandrapur) | 2 | 750 | 1500 | 50 km
14 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR ( from Nagpur) | 2 | 1000 | 2000 | 340km
15 | S1NH000363003 | BPCL PETROL PUMP, NEAR SBI, DHARANGAON, DIST. JALGAON - 425105 | 2 | 300 | 600 | 80 km
16 | S1NG000335013 | OPP. SANTOSHI MATA HALL, BHUSAWAL - 425201, DIST. JALGAON | 2 | 200 | 400 | 60 km
17 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | 2 | 500 | 1000 | 560 km
18 | S1NW000471067 | OPPOSITE VASANTDADA SAKHAR KARKHANA, MADHAVNAGAR ROAD, SANGLI 416416 | 2 | 600 | 1200 | 120 km
19 | S10A007249002 | ADITYA CORNER, TARABAI PARK, KOLHAPUR PIN 416003 | 2 | 200 | 400 | local
20 | S1NG020049028 | INSIDE SGGS COLLEGE PREMICES VISHNUPURI NANDED | 2 | 200 | 400 | local
21 | S1NG000454433 | DR. SUJATA RAVAT, 42/1, SHANTA CLINIC & GYM, NEAR SHIVRAJ SCHOOL, GANESH NAGAR, PUNE | 2 | 200 | 400 | local
22 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR ( from Nagpur) special visit with complete toolkit | 1 | 2000 | 2000 | 340km
23 | S1NG000298007 | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | 1 | 1000 | 1000 | 340 km
24 | S1NB001162008 | GANDHI CHOWK, NEAR HANUMAN MANDIR, NAVAPUR -425418, DIST. DHULE | 1 | 500 | 500 | 560 km
25 | S1NB001162008 | GANDHI CHOWK, NEAR HANUMAN MANDIR, NAVAPUR -425418, DIST. DHULE | 1 | 250 | 250 | - | New adpater installed
26 | S1NG000335012 | PANCHMUKHI MANDIR, JALGAON ROAD, BHUSAWAL - 425201, DIST. NASHIK | 1 | 300 | 900 | 70 km
27 | S1BG007249026 | GHODAVAT GROUP FACTORY, SANGLI ROAD, JAYSINGHPUR-416101 | 1 | 400 | 400 | 80 km
28 | S1BG007249144 | POLICE PETROL PUMP, BAVADA ROAD, OPP. NANA NANI PARK, TARABAI PARK, KOLHAPUR 416002 | 1 | 200 | 200 | local
29 | S1BH000311003 | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati 444601 | 2 | 500 | 1000 | local
30 | S1NC000311013 | Chandur Rly Road, near Wadali Garden, Amravati 444602 | 1 | 500 | 200 | local
31 | S1BG007249052 | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR-416002 | 1 | 450 | 450 | 380 km | Router Handover Ajeet Yadav | 2023-08-08
32 | S1BG000349014 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | 1 | 380 | 380 | 450 km | Router Handover Ajeet Yadav | 2023-08-08
33 | S1BH001469107 | ATM OWNER REQUESTED TO VACATE ATM LOBBY.NEW LOCATION STILL NOT FINALISED. | 1 | 350 | 350 | - | Router Handover Ajeet Yadav | 2023-08-08
34 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | 1 | 550 | 550 | 750 km | Router Handover Ajeet Yadav | 2023-08-08
35 | S1NW004711003 | ATM IS INRESTRICTED AREA OF ORDINANCE FACTORY, BHADRAWATI | 1 | 600 | 600 | 810 Km | Router Handover Ajeet Yadav | 2023-08-08
36 | S1BG001415002 | CAD PULGAON MILITARY CAMP, PULGAON | 1 | 400 | 400 | 680 Km | Router Handover Ajeet Yadav | 2023-08-08
37 | S1NG000335013 | OPP. SANTOSHI MATA HALL, BHUSAWAL - 425201, DIST. JALGAON | 1 | 450 | 450 | 410 Km | Router Handover Ajeet Yadav | 2023-08-08
38 | S1NG000298007 | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | 2 | 900 | 1800 | 250 km | - | -
39 | S1NG000298007 | RADHE BUILDINGCHAMROSHI ROAD GADCHIROLLI | 0 | 500 | 500 | 890 km | Router transporation charges ( From Pune to Nagpur GADCHIROLLI Site) | -
40 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 400 | 400 | 120 km | Yogesh vsited For Down Call with laptop | 2023-10-01
41 | S1NW000282007 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | 1 | 500 | 500 | 200 km | Sim card Replace | 2023-10-03
42 | S1BB006240136 | KAMOTHE SECTOR 20106, SION PANVEL EXPY, SECTOR 20,AISHWARYA AUTO STATIONKamothePanvel | 1 | - | - | - | UPS battery | 2023-09-30
43 | S1BG008851006 | NEAR TREASURY PANAJI BRANCH. | 1 | - | - | - | UPS battery | 2023-10-02
44 | S1NG000325008 | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR PIN 413411 | 1 | - | - | - | Area Power failure | 2023-10-04
45 | S1NW000325009 | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR 413411. | 1 | - | - | - | Area Power failure | 2023-10-04
46 | S1BH000311005 | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati 444606 (New adpater installed) | 1 | 750 | 750 | - | New adpater installed | 2023-10-04
47 | S1BB001252002 | WCL COLONY WAGHODA, SAONER | 1 | - | - | - | Area Power failure | 2023-10-05
48 | S1BG008851006 | NEAR TREASURY PANAJI BRANCH. | 1 | - | - | - | Van Welding Working | 2023-10-05
49 | Materials | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | 1 | 650 | 650 | - | Advantage To Sion Warehouse Materials (50 Router with full Set) | 2023-10-06
50 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 200 | 200 | - | Shutter Lock | 2023-10-08
51 | S1NG006240081 | SECTOR 21 NERULDOCTOR HOUSE, SECTOR 21,DOCTOR HOUSENavi Mumbai (M Corp.)Thane | 1 | - | - | - | Visit Atm Machine | 2023-10-11
52 | Materials | Sion jain Society Warehouse to Ghansholi MIDC Advantage OFFICE | 1 | 680 | 680 | - | Sion Warehouse To Advantage Materials (50 Router with full Set) | 2023-10-12
53 | S1BH007249023 | KORGAONKAR PETROL PUMP, SANGLI PHATA, SHIROLI, DIST. KOLHAPUR-416122 | 1 | - | - | - | Visit Done | 2023-10-12
54 | S1NW000282007 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | 1 | 450 | 450 | 200 km | Anil Shinde Visited with Laptop Service Call | 2023-10-13
55 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | - | - | - | Not Viisted | 2023-10-13
56 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | 1 | 500 | 500 | 80 Km | kiran Visited with Laptop Service Call | 2023-10-13
57 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 400 | 400 | 120 km | yogesh Patil Visited with Laptop Service Call | 2023-10-16
58 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 400 | 400 | 120 km | Yogesh Visit Done Configuration Done By Navnath | 2023-10-17
59 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 400 | 400 | 120 km | Yogesh Visit Done Configuration Done By Navnath | 2023-10-21
60 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | 1 | 350 | 350 | 20 km | Sanjay Visit at Site Antenna installation Done | 2023-10-27
61 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | 1 | 750 | 750 | 20 km | 3PIN Adopter installation by New Jio SIM Card to check feasibility. | 2023-11-03
62 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | 1 | 500 | 500 | 20 km | Anttena Relocated | 2023-11-04
63 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | 1 | 1500 | 1500 | 80 Km | Roshan visited at Site with Laptop for Service Call | 2023-11-04
64 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | 1 | 1500 | 1500 | 80 Km | New Router installation | 2023-11-06
65 | S1NW000282007 | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA - 416614 | 1 | 200 | 200 | 530 Km | Courier Charge from Mallavamn to Mumbai | 2023-11-06
66 | S1BH000311008 | Prof. Ram Meghe Square, Anjangaon Bari Road, Badnera 444701 | 1 | 500 | 500 | 80 KM | Utkarsha visited at Site with Laptop for Service Call | 2023-11-07
67 | S10F000393006 | JAMNER ROAD, NERI Naka, DIST. JALGAON, PIN - 424104 | 1 | 400 | 400 | 70 KM | jitrendra visited at Site with Laptop for Service Call | 2023-11-07
68 | S1BG007249026 | GHODAVAT GROUP FACTORY, SANGLI ROAD, JAYSINGHPUR-416101 | 1 | 600 | 600 | 90 Km | Shankar / Pradip visited at Site with Laptop for Service Call | 2023-11-07
69 | S1BG000300173 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | 1 | 2500 | 2500 | 30KM | Colaba Site New Installation | 2023-11-10
70 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | 1 | 1800 | 1800 | 520 Km | jitrendra visited at Site with Laptop for Service Call | 2023-11-16
71 | S1BG007249019 | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR 416005 | 1 | 350 | 350 | 35Km | Pradeep Patil visited at Site with Laptop for VPN Link Down call | 2023-11-16
72 | S1BB001252002 | WCL COLONY WAGHODA, SAONER Nagpur | 1 | 600 | 600 | 120 km | Ravi Dubey with Laptop for Service Call | 2023-11-20
73 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | 1 | 250 | 250 | 100 km | Harshal Pradeshi visited at Site | 2023-11-23
74 | S1NW020024001 | NEAR OLD POLICE STATION TAL HINGOLI | 1 | 700 | 700 | 75 KM | Santosh visited at site Router faulty (New Router Dispatch) | 2023-11-23
75 | S1BB001252002 | WCL COLONY WAGHODA, SAONER | 1 | 450 | 450 | 110 km | Ravi visited at site Router faulty (New Router Dispatch) | 2023-11-28
76 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | 1 | 900 | 900 | 250 Km | Dasrath Mishra visited at site Router faulty (New Router Dispatch) | 2023-11-28
77 | S1NB000501001 | NEAR ANANDVAN CHOWK, WARORA | 1 | 900 | 900 | 250 Km | Ravi Dubey visited at site Big 4G Antenna (10 meter wire) | 2023-11-26
78 | S1NB000501001 | NEAR ANANDVAN CHOWK, WARORA | 1 | 900 | 900 | 250 Km | Ravi Dubey visited at site New Router install | 2023-11-26
79 | S1BG000349015 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | 1 | 1500 | 1500 | 450 Km | Yohgesh Patil visited at site New Router install | 2023-11-27
80 | S1BW006240024 | VASHI RAILWAY STATIONVASHI RAILWAY STATION, NAVI MUMBAIVASHI RAILWAY STATIONNavi Mumbai (M Corp.)Thane | 1 | 0 | 0 | 30Km | Kissan visited at Site MCB Trip Up Site Online | 2023-11-27
81 | S1NG020039015 | JANTRE COMPLEX DHOKI ROAD KALAMB DIST OSMANABAD | 1 | 800 | 800 | 250 Km | Hamid Visited at site install router | 2023-11-30
82 | S1BB001252002 | WCL COLONY WAGHODA, SAONER | 1 | 450 | 450 | 110 km | Ravi visited at site for Service call with Laptop | 2023-12-01
83 | S1BW017554145 | NEAR HOTEL KAILASH VERUL AURANGABAD | 1 | 400 | 400 | 120 km | Yogesh Patil Joint Visit with CMS Engg | 2023-12-02
84 | S1BG003078002 | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY, BALLARPUR | 1 | 250 | 250 | 845 Km | 2Qnt 4G Antenna (3 meter wire) / 2 Pin_12 v Adopter (courier to Sion) | 2023-12-19
85 | S1BG000300173 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | 1 | 0 | 0 | 43 km | Vodafone SIM Card (9167468244 – 8991027390101102585) | 2023-11-17
86 | S1NB000501001 | NEAR ANANDVAN CHOWK, WARORA Nagpur | 1 | 500 | 500 | 776 km | AdV50 4G Router / 2 Pin_12 v Adopter (courier to Sion) | 2023-12-12
87 | S1BG000349015 | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana | 1 | Missing | Missing | 0 km | AdV50 4G Router / 2 Pin_12 v Adopter (courier to Sion) | Missing
88 | S1NB001162005 | NAGAR PALIKA COMPLEX, NAVAPUR - 425418 , DIST. DHULE | 1 | 200 | 200 | 330 km | AdV50 4G Router / 2 Pin_12 v Adopter (courier to Sion) | 2023-12-11
89 | S1NW020024001 | NEAR OLD POLICE STATION TAL HINGOLI | 1 | 180 | 180 | 589 km | AdV50 4G Router / 2 Pin_12 v Adopter(courier to Sion) | 2023-12-13
90 | S1BG000300173 | COLABA, MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI -400005 | 1 | 0 | 0 | 43 km | Vodafone SIM Card (9167468244 – 8991027390101102585) | 2023-12-11
91 | S1BB001252002 | WCL COLONY WAGHODA, SAONER Nagpur | 1 | 250 | 250 | 800 km | 2Qnt 4G Antenna (3 meter wire) (courier to Sion) | 2023-12-12
92 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | 1 | 500 | 500 | 80 Km | Roshan Visited with Laptop Service Call | 2024-01-06
93 | S1BW006240038 | OPP. APNA BAZAR VASHISECTOR 1, VASHIOPP APNA BAZAARNavi Mumbai (M Corp.)Thane | 1 | 0 | 0 | 20km | Kissan visited at Site with Laptop Service Call | 2024-01-09
94 | S1NG020027002 | BEED NAGAR ROAD NEAR COLLECTOR OFFICE BEED | 1 | 180 | 180 | 320 Km | Courier Charge from Beed to Mumbai | 2024-01-11
95 | S1NH000282008 | DAMBE BUILDING,TALERE BAZAAR, BELOW NEW FLY OVER, TALERE, MAHARASHTRA 416801 | 1 | 400 | 400 | 590 km | Courier Charge from Sindhadurg mallvan to Mumbai | 2024-01-11
96 | S1NW008851057 | SHRIDHAR APARTMENT COOP HSG SOC., SHOP NO 3, MERCES, NEAR MERCES GRAM PANCHAYAT, ILHAS GOA 403005 | 1 | 120 | 120 | 571 km | Courier Charge from GOA to Mumbai | 2024-01-11
97 | Materials | Ghansholi MIDC Advantage OFFICE to Sion jain Society Warehouse | 1 | 360 | 360 | - | Advantage To Sion Warehouse Materials (15 Router with full Set) | 2023-10-06
98 | S1NG003670003 | NEAR SHIVAJI CHOWK NILANGA TAL NILANGA DIST LATUR | 1 | 700 | 700 | - | Kunal Visited with Laptop Service Call | 2024-01-06
99 | S1NW015417161 | Amber Fort ,Jaipur 302028 | 1 | 350 | 350 | Akaram | Jio Sim Card locally Purchase | 2024-01-17
100 | S1NB006757004 | GUJJAR COMPLEX NEAR SHIVAJI CHOWK, GADCHANDUR | 1 | 700 | 700 | Santosh Swami | Kunal Visited with Laptop Service Call | 2024-01-30
101 | S1NG000335012 | PANCHMUKHI MANDIR, JALGAON ROAD, BHUSAWAL - 425201, DIST. NASHIK | 1 |  | 200 | - | - | 2024-02-16
102 | S1NG020049029 | INSIDE HUZUR SAHIB NANDED RAILWAY STATION PREMICES , NANDED RAILWATY STATION TAL DIST NANDED | 1 | 600 | 600 | - | - | 2024-02-17
103 | S10G011151001 | CRPF CAMPUS NANDED MUDKHED ROAD TAL MUDKHED DIST NANDED | 1 | 600 | 600 | - | Kishore Visited with Laptop Service Call | 2024-02-10
104 | S1BG006757002 | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR | 1 | 700 | 700 | Salim | Salim Vendor Visit Laptop service call (Miraz Technologies) | 2024-02-15
105 | S1BG000410001 | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE 410509. LANDKARK: OPP BHIMASHANKAR TEMPLE | 1 |  | 500 | 80 Km | kiran Visited with Laptop Service Call | 2024-02-12
67350

## CMS Traffic Installation (hidden)
Sr No | MSP | Allocation Date | Assigned By | Project | Vertical | code | SR # | Bank | ATMID | ATMID 2 | Site Type | Address | City | State | CSS BM | Installation Date
1 | AdvantageSB | 2023-08-04 | Sudhir S | - | Router | - | ADV50 | SBI | - | CMS Traffic Installation | ONSITE | Satya sai junction Indore | Indore | Madhya Pradesh | Yogesh Sani | 2023-10-04
2 | AdvantageSB | 2023-08-04 | Sudhir S | - | Router | - | "2120R502304260088 | SBI | - | CMS Traffic Installation | ONSITE | Palasia junction Indore | Indore | Madhya Pradesh | Yogesh Sani | 2023-10-08
3 | AdvantageSB | 2023-08-04 | Sudhir S | - | Router | - | ADV50 | SBI | - | CMS Traffic Installation | ONSITE | Shivaji vatiKa Chauraha Indore | Indore | Madhya Pradesh | Yogesh Sani | 2023-10-09
4 | AdvantageSB | 2023-08-04 | Sudhir S | - | Router | - | ADV50 | SBI | - | CMS Traffic Installation | ONSITE | Ghanta ghar Chauraha Indore | Indore | Madhya Pradesh | Yogesh Sani | 2023-10-08
5 | AdvantageSB | 2023-08-04 | Sudhir S | - | Router | - | "2120R502304260087 | SBI | - | CMS Traffic Installation | ONSITE | MR 9 Chauraha Indore | Indore | Madhya Pradesh | Yogesh Sani | 2023-10-09
6 | AdvantageSB | 2023-10-23 | Ajit Yadav | - | Router | - | ADV50 | SBI | - | CMS Traffic Installation | ONSITE | Stayam Nagar MIDC / Garware statium oppiste wakhard chowk Aurangabad. | Advantage | Maharashtra | Jakindra Pavare | 2023-10-25

## Warehouse materials (hidden)
Sr No | Requested By | Zone | Customer | Bank | Fencer-ID | ATM-ID | 2nd-ATM-ID | Complete-Site-Address | City | State | Pin-Code | CCS-BM | Product-Name | Product-Serial-Number | Vendor-Name | Product-Serial-Number | Dispatched Date | Dispatched Add | Material-Receiver-Name | Receiver-Mobile-Number | Invoice-Number | Courier-Name | Tracking-Number | Delivery-Status | Delivery-Date | Box | Pending-Material | Reason | Remark | Cost | Final Remark
1 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH000311003 | - | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati Pincode:- 444601 | Amravati | Maharashtra | 444601 | #REF! | 4G Router | 2120R502304260075 | CTS | 1 | 45147 | Utkarsh G Gajre 9923441558/9923055455 Rajveer", plot no 02, Vinit Layout, near Samruddhi heights, karan hardware road, Mangaldham Colony, Dastur Nagar, Amravati 444606 | Utkarsh G Gajre | 9923441558/9923055455 | Decleration | Trackon | 500340025547 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
2 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH000311010 | - | Deorankar Nagar, Kanwar Nagar, Guruchhaya Colony, Opp RK Bar& Restaurent, Samarth School Road, Amravati Pincode:- 444601 | Amravati | Maharashtra | 444601 | #REF! | 4G Router | 2120R502304260073 | CTS | 1 | 45147 | Utkarsh G Gajre 9923441558/9923055455 Rajveer", plot no 02, Vinit Layout, near Samruddhi heights, karan hardware road, Mangaldham Colony, Dastur Nagar, Amravati 444606 | Utkarsh G Gajre | 9923441558/9923055455 | Decleration | Trackon | 500340025547 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
3 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NC000311013 | - | Chandur Rly Road, near Wadali Garden, Amravati Pincode:- 444602 | Amravati | Maharashtra | 444602 | #REF! | 4G Router | 2120R502304260091 | CTS | 1 | 45147 | Utkarsh G Gajre 9923441558/9923055455 Rajveer", plot no 02, Vinit Layout, near Samruddhi heights, karan hardware road, Mangaldham Colony, Dastur Nagar, Amravati 444606 | Utkarsh G Gajre | 9923441558/9923055455 | Decleration | Trackon | 500340025547 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
4 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH000311005 | - | Gulshan Arcade, Railway Station Chouk, Bus Stand Road, Amravati Pincode:- 444606 | Amravati | Maharashtra | 444606 | #REF! | 4G Router | 2120R502304260162 | CTS | 1 | 45147 | Utkarsh G Gajre 9923441558/9923055455 Rajveer", plot no 02, Vinit Layout, near Samruddhi heights, karan hardware road, Mangaldham Colony, Dastur Nagar, Amravati 444606 | Utkarsh G Gajre | 9923441558/9923055455 | Decleration | Trackon | 500340025547 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
5 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH000311008 | - | Prof. Ram Meghe Square, Anjangaon Bari Road, Badnera Pincode:- 444701 | Amravati | Maharashtra | 444701 | #REF! | 4G Router | 2120R502304260069 | CTS | 1 | 45147 | Utkarsh G Gajre 9923441558/9923055455 Rajveer", plot no 02, Vinit Layout, near Samruddhi heights, karan hardware road, Mangaldham Colony, Dastur Nagar, Amravati 444606 | Utkarsh G Gajre | 9923441558/9923055455 | Decleration | Trackon | 500340025547 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
6 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BW017554056 | - | NEAR MORESHWAR IOCL PETROL PUMP SHAHAGUNJ AURANGABAD Pincode:- 431001 | Aurangabad | Maharashtra | 431001 | #REF! | 4G Router | 2120R502304260152 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
7 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW017554067 | - | NEAR SHENDRABAN PUMP SHAHAGUNJ AURANGABAD Pincode :-431001 | Aurangabad | Maharashtra | 431001 | #REF! | 4G Router | 2120R502304260117 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
8 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BW017554145 | - | NEAR HOTEL KAILASH VERUL AURANGABAD Pincode:- 431002 | Aurangabad | Maharashtra | 431002 | #REF! | 4G Router | 2120R502304260086 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
9 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG020029001 | - | NEAR SHIVAJI CHOWK AMBAJOGAI DIST BEED Pincode :- 431517 | Beed | Maharashtra | 431517 | #REF! | 4G Router | 2120R502304260066 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
10 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW020029003 | - | MONDHA ROAD TAL AMBAJOGAI DIST BEED Pincode :- 431517 | Beed | Maharashtra | 431517 | #REF! | 4G Router | 2120R502304260062 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
11 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW020962001 | - | NEAR SRT MEDICAL COLLEGE AMBAJOGAI BEED Pincode :- 431517 | Beed | Maharashtra | 431517 | #REF! | 4G Router | 2120R502304260124 | CTS | 1 | 45157 | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | JAKINDRA BHASKAR Pavhare7710016145Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | 0 | Decleration | overseasairfreight | 500340025898 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
12 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BW021332001 | - | Ambajogai- Ahmedpur road, Ghatnandur Pincode:- 431519 | Beed | Maharashtra | 431519 | #REF! | 4G Router | 2120R502304260061 | CTS | 1 | - | Jitendra Chaudhari | Jitendra Raju Chaudhari9325359264S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | #N/A | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 600 | Installed & Live
13 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG004711002 | - | NEAR BHADRAWATI ORDINANCE FACTORY MAIN GATE, BHADRAWATI Pincode :- 442501 | BHADRAWATI | Maharashtra | 442501 | #REF! | 4G Router | 2120R502304260105 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
14 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG000349015 | - | Jaistambh Chouk, Market Road, Opp Petrol Pump, Chikhli, Dist Buldhana Aurangabad Pincode:- 443201 | Buldhana | Maharashtra | 443201 | #REF! | 4G Router | 2120R502304260133 | CTS | 1 | 45147 | JAKINDRA BHASKAR 7710016145 Pavhare Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 7710016145 | Decleration | Trackon | 500340025565 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
15 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH000407003 | - | Railway Station Campus, Main Road, Khamgaon, Dist. Buldhana Pincode:- 444303 | Buldhana | Maharashtra | 444303 | #REF! | 4G Router | 2120R502304260157 | CTS | 1 | 45147 | JAKINDRA BHASKAR 7710016145 Pavhare Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 7710016145 | Decleration | Trackon | 500340025565 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
16 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH002176002 | - | SSGMCE, SBI Colony, Shegaon, Dist Buldhana Pincode:- 444203 | Buldhana | Maharashtra | 444203 | #REF! | 4G Router | 2120R502304260170 | CTS | 1 | 45147 | JAKINDRA BHASKAR 7710016145 Pavhare Plot no 13.Gut no 256.savitri nagar,gajanan nagar, near by Vitthal rukhmai mandir and Gajanan maharaj mandir ,savitrinagar chikhalthana Aurangabad 431001.maharashtra | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 7710016145 | Decleration | Trackon | 500340025565 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
17 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG006757001 | - | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR Chandrapur Pincode :- 442908 | Chandrapur | Maharashtra | 442908 | #REF! | 4G Router | 2120R502304260096 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
18 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG006757002 | - | NEAR MANIKGARH CEMENT FACTORY GATE, GADCHANDUR Chandrapur Pincode :- 442908 | Chandrapur | Maharashtra | 442908 | #REF! | 4G Router | 2120R502304260123 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
19 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG003078002 | - | BALLARPUR PAPER MILL GATE NO 2 PAPER MILL COLONY,Chandrapur Pincode:- 442402 | Chandrapur | Maharashtra | 442402 | #REF! | 4G Router | 2120R502304260074 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
20 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB006757004 | - | GUJJAR COMPLEX NEAR SHIVAJI CHOWK, GADCHANDUR Chandrapur Pincode:-442908 | Chandrapur | Maharashtra | 442908 | #REF! | 4G Router | 2120R502304260141 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
21 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB000501001 | - | NEAR ANANDVAN CHOWK, WARORA Chandrapur Pincode:- 442914 | Chandrapur | Maharashtra | 442914 | #REF! | 4G Router | 2120R502304260164 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
22 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB001162005 | - | NAGAR PALIKA COMPLEX, NAVAPUR DIST. DHULE Pincode:- 425418 | Dhule | Maharashtra | 425418 | #REF! | 4G Router | 2120R502304260180 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
23 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB001162006 | - | NAGAR PALIKA COMPLEX, NAVAPUR DIST. DHULE Pincode:- 425418 | Dhule | Maharashtra | 425418 | #REF! | 4G Router | 2120R502304260172 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
24 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB001162008 | - | GANDHI CHOWK, NEAR HANUMAN MANDIR, NAVAPUR Pincode:- 425418 | Dhule | Maharashtra | 425418 | #REF! | 4G Router | 2120R502304260119 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
25 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB001162007 | - | MAIN ROAD, OPP. SBI, NAVAPUR , DIST. DHULE Pincode:-425418 | Dhule | Maharashtra | 425418 | #REF! | 4G Router | 2120R502304260166 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
26 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW020024001 | - | NEAR OLD POLICE STATION TAL HINGOLI Pincode :-431513 | HINGOLI | Maharashtra | 431513 | #REF! | 4G Router | 2120R502304260072 | CTS | 1 | 45159 | Punjabrao Avchar 7020545399 Manka Complex Mahesh Chowk Hingoli 431513 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 7020545399 | Decleration | Pending to Dispatch | Delivered | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
27 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH000441014 | - | SARDAR VALLABH PATEL ROAD, JALGAON Pincode:- 424201 | Jalgaon | Maharashtra | 424201 | #REF! | 4G Router | 2120R502304260173 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
28 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000272002 | - | SATOD ROAD, TEHSIL- YAVAL, DIST. JALGAON Pincode:- 425301 | Jalgaon | Maharashtra | 425301 | #REF! | 4G Router | 2120R502304260154 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
29 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH000363003 | - | BPCL PETROL PUMP, NEAR SBI, DHARANGAON, DIST. JALGAON Pincode:- 425105 | Jalgaon | Maharashtra | 425105 | #REF! | 4G Router | 2120R502304260120 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
30 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10F000393006 | - | JAMNER ROAD, NERI, DIST. JALGAON Pincode:- 424104 | Jalgaon | Maharashtra | 424104 | #REF! | 4G Router | 2120R502304260143 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
31 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH001207004 | - | MARWADI LANE, ERANDOL, DIST. JALGAON , ERANDOL Pincode:- 425109 | Jalgaon | Maharashtra | 425109 | #REF! | 4G Router | 2120R502304260144 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
32 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000335013 | - | OPP. SANTOSHI MATA HALL, BHUSAWAL JALGAON Pincode:- 425201 | Jalgaon | Maharashtra | 425201 | #REF! | 4G Router | 2120R502304260158 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
33 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG000335030 | - | SBI BHUSAWAL MAIN BRANCH, BHUSAWAL , DIST. JALGAON Pincode:- 425201 | Jalgaon | Maharashtra | 425201 | #REF! | 4G Router | 2120R502304260142 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
34 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10A000393004 | - | RAILWAY STATION, JALGAON Pincode:- 425002 | Jalgaon | Maharashtra | 425002 | #REF! | 4G Router | 2120R502304260128 | CTS | 1 | 45157 | Jitendra Raju Chaudhari9325359264S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Jitendra Raju Chaudhari9325359264S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | 0 | Decleration | overseasairfreight | 2366579353 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
35 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249018 | - | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR Pincode:- 416005 | Kolhapur | Maharashtra | 416005 | #REF! | 4G Router | 2120R502304260099 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
36 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249019 | - | DABOLKAR CORNER NEAR ROYAL PLAZA S T STAND KOLHAPUR Pincode:- 416005 | Kolhapur | Maharashtra | 416005 | #REF! | 4G Router | 2120R502304260174 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
37 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249021 | - | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR Pincode:- 416002 | Kolhapur | Maharashtra | 416002 | #REF! | 4G Router | 2120R502304260098 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
38 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249052 | - | HPCL PETROL PUMP, OPP. PARVATI THEATRE, UDHYAMNAGAR INDUSTRIAL ESTATE, KOLHAPUR Pincode:- 416002 | Kolhapur | Maharashtra | 416002 | #REF! | 4G Router | 2120R502304260179 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
39 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10A007249002 | - | ADITYA CORNER, TARABAI PARK, KOLHAPUR Pincode:- 416003 | Kolhapur | Maharashtra | 416003 | #REF! | 4G Router | 2120R502304260163 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
40 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG007249064 | - | BPC PETROLINK A/P KUMBHOJ TALUKA HATKALANGALE DISTRICT KOLHAPUR Pincode:- 416111 | Kolhapur | Maharashtra | 416111 | #REF! | 4G Router | 2120R502304260135 | CTS | 1 | 45148 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Trackon | 2366579209 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
41 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249057 | - | CPR HOSPITAL CAMPUS, KOLHAPUR Pincode:- 416002 | Kolhapur | Maharashtra | 416002 | #REF! | 4G Router | 2120R502304260121 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
42 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH007249023 | - | KORGAONKAR PETROL PUMP, SANGLI PHATA, SHIROLI, DIST. KOLHAPUR Pincode:- 416122 | Kolhapur | Maharashtra | 416122 | #REF! | 4G Router | 2120R502304260167 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
43 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249059 | - | KRISHNA PETROLEUM, BPCL, TAKALA AREA, KOLHAPUR Pincode:- 416008 | Kolhapur | Maharashtra | 416008 | #REF! | 4G Router | 2120R502304260151 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
44 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249144 | - | POLICE PETROL PUMP, BAVADA ROAD, OPP. NANA NANI PARK, TARABAI PARK, KOLHAPUR Pincode:- 416002 | Kolhapur | Maharashtra | 416002 | #REF! | 4G Router | 2120R502304260134 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
45 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249053 | - | RATNA PETROLEUM, NEW WASHI NAKA, RADHANAGARI ROAD, KOLHAPUR Pincode:- 416002 | Kolhapur | Maharashtra | 416002 | #REF! | 4G Router | 2120R502304260089 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
46 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG007249026 | - | GHODAVAT GROUP FACTORY, SANGLI ROAD, JAYSINGHPUR Kolhapur Pincode:- 416101 | Kolhapur | Maharashtra | 416101 | #REF! | 4G Router | 2120R502304260165 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
47 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020037010 | - | INSIDE GOVERNMENT MEDICAL COLLEGE LATUR Pincode:- 413512 | Latur | Maharashtra | 413512 | #REF! | 4G Router | 2120R502304260178 | CTS | 1 | 45157 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 0 | Decleration | overseasairfreight | 500340025880 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
48 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG003670003 | - | NEAR SHIVAJI CHOWK NILANGA TAL DIST LATUR Pincode:- 413521 | Latur | Maharashtra | 413521 | #REF! | 4G Router | 2120R502304260082 | CTS | 1 | 45157 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 0 | Decleration | overseasairfreight | 500340025880 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
49 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000298007 | - | RADHE BUILDING CHAMROSHI ROAD GADCHIROLLI Nagpur Pincode :- 442605 | Nagpur | Maharashtra | 442605 | #REF! | 4G Router | 2120R502304260108 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Ravi Dubey | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
50 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG011420001 | - | BHIWAPUR,INFRONT OF SBI BHIWAPUR BRANCH, TAH.UMRED DEIS- NAGPUR Pincode:- 441201 | Nagpur | Maharashtra | 441201 | #REF! | 4G Router | 2120R502304260161 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Ravi Dubey | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
51 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BB001252002 | - | WCL COLONY WAGHODA, SAONER Nagpur Pincode :- 441107 | Nagpur | Maharashtra | 441107 | #REF! | 4G Router | 2120R502304260070 | CTS | 1 | 45147 | Ravi Dubey 9158434514 C/O Chandra Prakash Dubey Plot No : 9/A Jai Gurudev Nagar, Near Besa Road, Manewada Post Bhagwan Nagar Nagpur 440027 | Ravi Dubey | 9158434514 | Decleration | Delivery.com | 12364010164861 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
52 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10G011151001 | - | CRPF CAMPUS NANDED MUDKHED ROAD TAL MUDKHED DIST NANDED Pincode :-431806 | NANDED | Maharashtra | 431806 | #REF! | 4G Router | 2120R502304260065 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
53 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020049029 | - | INSIDE HUZUR SAHIB NANDED RAILWAY STATION PREMICES ,NANDED Pincode:- 431601 | NANDED | Maharashtra | 431601 | #REF! | 4G Router | 2120R502304260129 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
54 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020049028 | - | INSIDE SGGS COLLEGE PREMICES VISHNUPURI NANDED Pincode :- 431606 | NANDED | Maharashtra | 431606 | #REF! | 4G Router | 2120R502304260177 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
55 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020056001 | - | SHIVAJI CHOWK NEAR STATE BANK OF INDIA KANDHAR NANDED Pincode :- 431714 | NANDED | Maharashtra | 431714 | #REF! | 4G Router | 2120R502304260127 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
56 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020049018 | - | ZILLA PARISHAD MAIN BUILDING OPP SHIVAJI MAHARAJ STATUE RAILWAY STATION ROAD NANDED Pincode :- 431601 | NANDED | Maharashtra | 431601 | #REF! | 4G Router | 2120R502304260083 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
57 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000435019 | - | LAL BAHADUR SHASTRI MARKET, NANDURBAR Pincode:-425412 | NANDURBAR | Maharashtra | 425412 | #REF! | 4G Router | 2120R502304260084 | CTS | 1 | 45147 | Jitendra Raju Chaudhari 9325359264 S.NO 78/3 4A 4B P.NO 37 NEAR DNC COLLEGE SHANKARRAO NAGAR 425001 | Jitendra Raju Chaudhari | 9325359264 | Decleration | Delivery.com | 12364010164850 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
58 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BH001469028 | - | 493/267, SATPUR GANGAPUR LINK ROAD , ASHOK NAGAR, NASHIK Pincode:- 422012 | Nashik | Maharashtra | 422012 | #REF! | 4G Router | 2120R502304260095 | CTS | 1 | 45145 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 600 | Installed & Live
59 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG005392007 | - | NEAR GANGADHAR TALKIES, AT POST SINNAR , DIST NASHIK Pincode:- 422103 | Nashik | Maharashtra | 422103 | #REF! | 4G Router | 2120R502304260176 | CTS | 1 | 45145 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 600 | Installed & Live
60 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BW001469101 | - | POOJA AVENUE, SHANTI PARK, UPNAGAR, NASHIK Pincode:- 422006 | Nashik | Maharashtra | 422006 | #REF! | 4G Router | 2120R502304260116 | CTS | 1 | 45145 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 600 | Installed & Live
61 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BA000440001 | - | YEOLA ROAD, AT POST - VINCHUR, DIST. NASHIK Pincode:- 422306 | Nashik | Maharashtra | 422306 | #REF! | 4G Router | 2120R502304260126 | CTS | 1 | 45145 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | Bharat P / 9923304111 / N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 600 | Installed & Live
62 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000335012 | - | PANCHMUKHI MANDIR, Nashik JALGAON ROAD, BHUSAWAL Pincode :-425201 | BHUSAWAL | Maharashtra | 425201 | #REF! | 4G Router | 2120R502304260092 | CTS | 1 | 45147 | Bharat Ambarsing Pardeshi 7385703769 / 9657765388 N42/C/F3/20/6 CIDCO Ashtvinayak chauk behind Ganpati Mandir Navjivan High school 4ThNASIK NASHIK 422009 | Bharat Ambarsing Pardeshi | 7385703769 / 9657765388 | Decleration | Trackon | 2366579200 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
63 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG008851009 | - | GOA MEDICAL COLLEGE, BAMBOLIM, TISWADI GOA Pincode:- 403202 | North Goa | Maharashtra | 403202 | #REF! | 4G Router | 2120R502304260150 | CTS | 1 | 45157 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | 0 | Decleration | overseasairfreight | 500340025871 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
64 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG008851006 | - | NEAR TREASURY PANAJI BRANCH Goa Pincode :- 403001 | North Goa | Maharashtra | 403001 | #REF! | 4G Router | 2120R502304260068 | CTS | 1 | 45157 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | Harendra Singh8208922801C/O Antonio Fernandes h.no.718 Flat no.1 2nd floor Antonio Fernandes building malbhat Margao Goa 403601 | 0 | Decleration | overseasairfreight | 500340025871 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
65 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG020039015 | - | JANTRE COMPLEX DHOKI ROAD KALAMB DIST OSMANABAD Pincode:- 413507 | OSMANABAD | Maharashtra | 413507 | #REF! | 4G Router | 2120R502304260104 | CTS | 1 | 45157 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 0 | Decleration | overseasairfreight | 500340025880 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
66 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NH020047001 | - | MAIN ROAD PARANDA DIST OSMANABAD Pincode :- 413502 | OSMANABAD | Maharashtra | 413502 | #REF! | 4G Router | 2120R502304260100 | CTS | 1 | 45157 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid9503707672JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | 0 | Decleration | overseasairfreight | 500340025880 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
67 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW003667003 | - | NEAR PEDHA HANUMAN TEMPLE PARBHANI Pincode :- 431401 | PARABHANI | Maharashtra | 431401 | #REF! | 4G Router | 2120R502304260094 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
68 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NB003667026 | - | NEAR PEDHA HANUMAN TEMPLE PARBHANI Pincode :- 431401 | PARABHANI | Maharashtra | 431401 | #REF! | 4G Router | 2120R502304260102 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
69 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG009905003 | - | NEAR DEOGAON PHATA JINTUR MANTA HIGHWAY AT POST DEOGAON TAL SAILU PARABHANI Pincode :- 431509 | PARABHANI | Maharashtra | 431509 | #REF! | 4G Router | 2120R502304260115 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
70 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG003667028 | - | NEAR RAILWAY STATION PARABHANI Pincode :- 431401 | PARABHANI | Maharashtra | 431401 | #REF! | 4G Router | 2120R502304260106 | CTS | 1 | 45157 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | Kishore Bhadure9767711023Govind nagar,Taroda BK, Nanded, Maharashtra - 431605 | 0 | Decleration | overseasairfreight | 17942710003010 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
71 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG000410001 | - | C/OO SHRI SURESH KONDHARE, SHRI KSHETRA BHIMASHANKAR, TAL KHED, PUNE Pincode :- 410509 | Pune | Maharashtra | 410509 | #REF! | 4G Router | 2120R502304260093 | CTS | 1 | 45145 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
72 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000454433 | - | DR. SUJATA RAVAT, 42/1, SHANTA CLINIC & GYM, NEAR SHIVRAJ SCHOOL, GANESH NAGAR, PUNE Pin Code :- 411014 | Pune | Maharashtra | 411014 | #REF! | 4G Router | 2120R502304260118 | CTS | 1 | 45145 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
73 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BB000410003 | - | KRISHI UTPANN BAJAR SAMITI, CHHANTRAPATI SHIVAJI MARKET YARD, RAJGURUNAGAR (KHED), PUNE Pincode:- 410505 | Pune | Maharashtra | 410505 | #REF! | 4G Router | 2120R502304260107 | CTS | 1 | 45145 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
74 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW000454187 | - | SHOP NO.A/7, ARJUN PARK, KALE-PADAL ROAD, SASANENAGAR, PUNE Pincode:- 411028 | Pune | Maharashtra | 411028 | #REF! | 4G Router | 2120R502304260071 | CTS | 1 | 45145 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | Kailash R / Annu 9552384808 / Clear Secured Services Pvt. Ltd. Amit Complex 474,Office No .2 , 2nd floor ,Oppsite New English School , Sadashiv Peth , Pune - 411030 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
75 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000555005 | - | THE LONAWALA INDUSTRIAL ESTATE CO-OPERATIVE LTD. LONAWALA Pincode:- 410401 | Pune | Maharashtra | 410401 | #REF! | 4G Router | 2120R502304260153 | CTS | 1 | 45145 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | Roshan prakash phalke. Couriar Address:-A/p - Yelwadi(chakan - talegaon road )near dehu phata tal -rajgurunagar pune 412109 . 7756025837 | 0 | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
76 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10B007339003 | - | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune Pincode:- 411606 | Pune | Maharashtra | 411606 | #REF! | 4G Router | 2120R502304260131 | CTS | 1 | - | #N/A | #N/A | #N/A | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
77 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BB007339004 | - | University Road(Pune) Branch (07339) Veer Chaphekar Chowk,1154, Shivajinagar, Pune Pincode:- 411606 | Pune | Maharashtra | 411606 | #REF! | 4G Router | 2120R502304260097 | CTS | 1 | - | #N/A | #N/A | #N/A | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 550 | Installed & Live
78 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000527005 | - | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI Pincode:- 415311 | Sangli | Maharashtra | 415311 | #REF! | 4G Router | 2120R502304260156 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
79 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000527006 | - | RADKAKRISHNA COMPLEX, OPP. ST STAND, A/P VITA, DIST. SANGLI Pincode:- 415311 | Sangli | Maharashtra | 415311 | #REF! | 4G Router | 2120R502304260171 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
80 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000527007 | - | NEAR GANAPATI TEMPLE, GURUWAR PETH, A/P. TASGAON, DIST. SANGLI Pincode:- 416312 | Sangli | Maharashtra | 416312 | #REF! | 4G Router | 2120R502304260147 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
81 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW000471067 | - | OPPOSITE VASANTDADA SAKHAR KARKHANA, MADHAVNAGAR ROAD, SANGLI Pincode:- 416416 | Sangli | Maharashtra | 416416 | #REF! | 4G Router | 2120R502304260110 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
82 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BG000471063 | - | SP OFFICE, SANGLI, VISHRAMBAG, SANGLI Pincode:- 416416 | Sangli | Maharashtra | 416416 | #REF! | 4G Router | 2120R502304260101 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
83 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW000471068 | - | ZULELAL CHOWK, NEAR S T STAND SANGLI Pincode:- 416416 | Sangli | Maharashtra | 416416 | #REF! | 4G Router | 2120R502304260140 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
84 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S10G001372001 | - | C/O SHRI RAMCHANDRA PANDURANG RAUT, A/P PATAN, LIBRARY CHOWK, PATAN, DIST. SATARA Pincode:- 415206 | SATARA | Maharashtra | 415206 | #REF! | 4G Router | 2120R502304260169 | CTS | 1 | 45147 | Shankar Gadkar (9975595458 ) Swamini Footwear, Shop No3, Bhairavnath Complex, survey Colony Radhanagri Road, Saneguruji Vasahat, Kolhapur, Kolhapur 416012 | Shankar Gadkar | 9975595458 | Decleration | Delivery.com | 12364010164846 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
85 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW000282007 | - | FERNANDES GALA, MALVAN ROAD, ACHARE TITHA, ACHARE, MALVAN MAHARASHTRA Pincode:- 416614 | SINDHUDURG | Maharashtra | 416614 | #REF! | 4G Router | 2120R502304260155 | CTS | 1 | 45157 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | 0 | Decleration | overseasairfreight | 17255810043234 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
86 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BC000495001 | - | HOTEL LAUKIK BLDG, BAZARPETH ROAD, VENGURLA, SINDHUDURG, MAHARASHTRA Pincode:- 416516 | SINDHUDURG | Maharashtra | 416516 | #REF! | 4G Router | 2120R502304260175 | CTS | 1 | 45157 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | Anil Shinde963770487830.Bajarpeth Behind fashion. House Rajapur. Pin Code 416702 | 0 | Decleration | overseasairfreight | 17255810043234 | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
87 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NG000325008 | - | MOHAN KUNJ , PARANDA ROAD BARSHI SOLAPUR Pincode:- 413411 | Solapur | Maharashtra | 413411 | #REF! | 4G Router | 2120R502304260145 | CTS | 1 | 45147 | Hamid 9503707672 JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid | 9503707672 | Decleration | Trackon | 500340025574 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
88 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1NW000325009 | - | NEAR S T STAND, TULJAPUR ROAD, OPP. SBI BARSHI BRANCH, BARSHI DIST. SOLAPUR Pincode:- 413411 | Solapur | Maharashtra | 413411 | #REF! | 4G Router | 2120R502304260148 | CTS | 1 | 45147 | Hamid 9503707672 JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid | 9503707672 | Decleration | Trackon | 500340025574 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
89 | Sandeep Prajapati | West | Advantage SB | SBI | NA | S1BW000483058 | - | Survey no 110/1b , Sant Tukaram nagar, Vijapur Road, Solapur Pincode:- 413004 | Solapur | Maharashtra | 413004 | #REF! | 4G Router | 2120R502304260112 | CTS | 1 | 45147 | Hamid 9503707672 JayMahalaxmiNagar,JuleSolapur,NearGirijaMangalkaryalay,Solapur413004 | Hamid | 9503707672 | Decleration | Trackon | 500340025574 | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
90 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BW006240024 | - | VASHI RAILWAY STATION Near Raghuleela Mall Navi Mumbai Pin Code :- 400703 | Mumbai Metro | Mumbai Metro | 400703 | #REF! | 4G Router | 2120R502304260146 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
91 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BW006240018 | - | SANPADA RLY STN ATM-2 ABHISHEK CHS, SECTOR:- 30 SANPADA (W) Navi Mumbai Pin Code :- 400705 | Mumbai Metro | Mumbai Metro | 400705 | #REF! | 4G Router | 2120R502304260080 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
92 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BW006240038 | - | OPP. APNA BAZAR VASHI SECTOR 1, Navi Mumbai Pincode :- 400610 | Mumbai Metro | Mumbai Metro | 400610 | #REF! | 4G Router | 2120R502304260103 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
93 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BG006240020 | - | Sector 9, KHANDA COLONY Navi Mumbai Panvel Pincode :- 410206 | Mumbai Metro | Mumbai Metro | 410206 | #REF! | 4G Router | 2120R502304260078 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
94 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BH006240019 | - | Sector 9, KHANDA COLONY Navi Mumbai Panvel Pincode :- 410206 | Mumbai Metro | Mumbai Metro | 410206 | #REF! | 4G Router | 2120R502304260159 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
95 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BB006240136 | - | 106, SION PANVEL EXPY, SECTOR 20,AISHWARYA AUTO STATION Navi Mumbai Kamothe Pincode :- 410210 | Mumbai Metro | Mumbai Metro | 410210 | #REF! | 4G Router | 2120R502304260085 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
96 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1NW006240014 | - | SBOA PUBLIC SCHOOL ,AYYAPPA RD,DR D Y PATIL VIDYANAGAR, NERUL Navi Mumbai Pincode :- 400706 | Mumbai Metro | Mumbai Metro | 400706 | #REF! | 4G Router | 2120R502304260063 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
97 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1NG006240081 | - | SECTOR 21, DOCTOR HOUSE, NERUL Navi Mumbai Pincode :- 400706 | Mumbai Metro | Mumbai Metro | 400706 | #REF! | 4G Router | 2120R502304260113 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
98 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BB006240040 | - | JNPT SBI Sheva Navi Mumbai Uran Pincode :- 400707 | Mumbai Metro | Mumbai Metro | 400707 | #REF! | 4G Router | 2120R502304260064 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
99 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BW006240101 | - | SBI ATM URAN GAON Nagaon Uran Pincode :- 400702 | Mumbai Metro | Mumbai Metro | 400702 | #REF! | 4G Router | 2120R502304260125 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | By Hand | By Hand | By Hand | Deliver |  |  | No Pending Materials |  |  | 200 | Installed & Live
100 | Sandeep Prajapati | South | Advantage SB | SBI | NA | S1BG000300173 | - | COLABA MILITARY STATION, HEAD QUARTERS MG & G AREA, ASSAYE BUILDING, COLABA MUMBAI Pincode :-400005 | MUMBAI METRO | Mumbai Metro | 400005 | #REF! | 4G Router | 2120R502309010127 | CTS | 1 | - | BY Hand | BY Hand | BY Hand | Decleration | By Bus | By Bus | Deliver |  |  | No Pending Materials |  |  | 150 | Installed & Live
101 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NB006094001 | - | SBI MOBILE ATM VAN, ALWAR | ALWAR | RAJASTHAN | 301001 | Pradhan Meena | 4G Router | 2120R502309180209 | CTS | 1 | 45302 | Ashish Sharma (9024134426) s/o Girraj Prasad sharma-out side hazuri gate alwar 301001 | Ashish Sharma | 9024134426 | Decleration | Trackon | 2371597347 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | S1NB006094001 install on Other ATM S1NW006094058 | 200 | Installed & Live
L | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW000712015 | - | Village Bhadwa , Tahsil Kishangarh Renwal | JAIPUR | RAJASTHAN | 303328 | Pradhan Meena | 4G Router | 2120R502309180203 | CTS | 1 | 45302 | Jaip Shanker Yadav (8949551732) Plot n. 26 laxmi nagar hatwara road opp. ESIC hospital 4 n. dispancry sodala Jaipur,302006 | Jaip Shanker Yadav | 8949551732 | Decleration | Trackon | 500384556188 | Deliver | 2024-01-17 | 1 | No Pending Materials |  | S1BW000712015 install on Other ATM S1NG031036003 | 200 | Installed & Live
103 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW032090098 | - | HPCL PETROL PUMP, KALWAR ROAD, JAIPUR, RAJASTHAN, 300205 | JAIPUR | RAJASTHAN | 302012 | Pradhan Meena | 4G Router | 2120R502309180216 | CTS | 1 | 45302 | Jaip Shanker Yadav (8949551732) Plot n. 26 laxmi nagar hatwara road opp. ESIC hospital 4 n. dispancry sodala Jaipur,302006 | Jaip Shanker Yadav | 8949551732 | Decleration | Trackon | 500384556188 | Deliver | 2024-01-17 | 1 | No Pending Materials |  | S1BW032090098 install on Other ATM S1BB032090102 | 200 | WIP
104 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW032090113 | - | MOBILE ATM,JAIPUR,RAJASTHAN,300205 | JAIPUR | RAJASTHAN | 302005 | Pradhan Meena | 4G Router | 2120R502309180357 | CTS | 1 | 45302 | Jaip Shanker Yadav (8949551732) Plot n. 26 laxmi nagar hatwara road opp. ESIC hospital 4 n. dispancry sodala Jaipur,302006 | Jaip Shanker Yadav | 8949551732 | Decleration | Trackon | 500384556188 | Deliver | 2024-01-17 | 1 | No Pending Materials |  | S1BW032090113 install on Other ATM S1NW015417161 | 200 | Installed & Live
105 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW015417293 | - | SBI MOBILE ATM VAN, JAIPUR | JAIPUR | RAJASTHAN | 302015 | Pradhan Meena | 4G Router | 2120R502309180355 | CTS | 1 | 45302 | Jaip Shanker Yadav (8949551732) Plot n. 26 laxmi nagar hatwara road opp. ESIC hospital 4 n. dispancry sodala Jaipur,302006 | Jaip Shanker Yadav | 8949551732 | Decleration | Trackon | 500384556188 | Deliver | 2024-01-17 | 1 | No Pending Materials |  | S1BW015417293 install on Other ATM S1BW032090129 | 200 | Installed & Live
106 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NB032090247 | - | POLO VICTORY JAIPUR | JAIPUR | RAJASTHAN | 302001 | Pradhan Meena | 4G Router | 2120R502309180256 | CTS | 1 | 45302 | Jaip Shanker Yadav (8949551732) Plot n. 26 laxmi nagar hatwara road opp. ESIC hospital 4 n. dispancry sodala Jaipur,302006 | Jaip Shanker Yadav | 8949551732 | Decleration | Trackon | 500384556188 | Deliver | 2024-01-17 | 1 | No Pending Materials |  | S1NB032090247 install on Other ATM S1NG031036004 | 200
107 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603009 | - | SBI BRANCH, OPP. RAILWAY STATION, AJMER | AJMER | RAJASTHAN | 305001 | Pradhan Meena | 4G Router | 2120R502309180160 | CTS | 1 | 45302 | C/o Manoj Choudhary (7414037556 ) H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | Decleration | Trackon | 500384556170 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | S1BG000603009 install on Other ATM S1NG002424007 | 200 | Deliver (Installation Schedule Pending)
108 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BB031104029 | - | SBI MOBILE ATM VAN, AJMER | AJMER | RAJASTHAN | 305001 | Pradhan Meena | 4G Router | 2120R502309180114 | CTS | 1 | 45302 | C/o Manoj Choudhary (7414037556 ) H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | Decleration | Trackon | 500384556170 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | on Same Site S1BB031104029 install | 200 | Installed & Live
109 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW000603049 | - | NEAR BAJRANG TEMPLE,CAC AJMER | AJMER | RAJASTHAN | 305001 | Pradhan Meena | 4G Router | 2120R502309180361 | CTS | 1 | 45302 | C/o Manoj Choudhary (7414037556 ) H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | Decleration | Trackon | 500384556170 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | S1NW000603049 install on Other ATM S1NW006335001 | 200 | Installed & Live
110 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG031076012 | - | Police Line Karauli | Karauli | RAJASTHAN | 322241 | Pradhan Meena | 4G Router | 2120R502309180254 | CTS | 1 | 45302 | Rajendra meena (7992141431) s/o mangy ram meena gram post pahadi tehsil todabhim dist. Gangapur 322238 | Rajendra meena | 7992141431 | Decleration | https://overseasairfreight.com/ | 17255810063626 | In Transit | Deliver | 1 | No Pending Materials |  | Deliver (Installation Schedule Pending) | 200 | Deliver (Installation Schedule Pending)
111 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BB031252062 | - | SBI MOBILE ATM VAN, KOTA | KOTA | RAJASTHAN | 324007 | Pradhan Meena | 4G Router | 2120R502309180214 | CTS | 1 | 45302 | Jai shyam malav (8118866181) A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | Decleration | Trackon | 2371597345 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | on Same Site S1BB031252062 install | 200 | Installed & Live
112 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031237029 | - | NEW COURT PREMISES NIMBAHERA ROAD CHITTORGARH | CHITTORGARH | RAJASTHAN | 312001 | Pradhan Meena | 4G Router | 2120R502309180158 | CTS | 1 | 45302 | C/o Manoj Choudhary (7414037556 ) H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | Decleration | Trackon | 500384556170 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | S1BW031237029 install on Other ATM S1NG006335023 | 200 | Installed & Live
113 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BB031162015 | - | SBI MOBILE ATM VAN, BIKANER | BIKANER | RAJASTHAN | 334001 | Pradhan Meena | 4G Router | 2120R502309180180 | CTS | 1 | 45302 | Dharmaram chaudhary (7568185165) Road n. 5 cinemagic ke samne kayam nagar bikaner 334001 | Dharmaram chaudhary | 7568185165 | Decleration | Trackon | 2371597348 | Deliver | 2024-01-18 |  | No Pending Materials |  | on Same Site S1BB031162015 install | 200 | Installed & Live
114 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NB015415039 | - | SBI MOBILE ATM VAN, JALORI GATE, JODHPUR | JODHPUR | RAJASTHAN | 342001 | Pradhan Meena | 4G Router | 2120R502309180212 | CTS | 1 | 45302 | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | Decleration | Trackon | 2371597346 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | on Same Site S1NB015415039 install | 200 | Installed & Live
115 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG031589027 | - | Government Medical College, Pali | PALI | RAJASTHAN | 306401 | Pradhan Meena | 4G Router | 2120R502309180291 | CTS | 1 | 45302 | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | Decleration | Trackon | 2371597346 | Deliver | 2024-01-18 | 1 | No Pending Materials |  | S1NB031589027 install on Other ATM S1NW015415465 | 200 | Installed & Live
116 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW031252100 | - | SANTOSHI NAGAR, KESHAVPURA, KOTA324007 | KOTA | Kota | 324007 | SANTOSHI NAGAR, KESHAVPURA, KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
117 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603094 | - | HP PETROL PUMP, AGRA GATE, PR MARG, AJMER305001 | AJMER | Ajmer | 305001 | HP PETROL PUMP, AGRA GATE, PR MARG, AJMER305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
118 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW000603011 | - | POLICE LINE AJMER305001 | AJMER | Ajmer | 305001 | POLICE LINE AJMER305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
119 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031252019 | - | S-132, INDIRA VIHAR, CAC, K, KOTA, RAJASTHAN, 324007324007 | KOTA | Kota | 324007 | S-132, INDIRA VIHAR, CAC, K, KOTA, RAJASTHAN, 324007324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
120 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031252025 | - | STATE BANK OF INDIA, 3K, TAL MANDI, OPP. KHANDELWAL NURSING HOME, KOTA324007 | KOTA | Kota | 324007 | STATE BANK OF INDIA, 3K, TAL MANDI, OPP. KHANDELWAL NURSING HOME, KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
121 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415048 | - | MANDORE ROAD, JODHPUR342001 | JODHPUR | Jodhpur | 342001 | MANDORE ROAD, JODHPUR342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
122 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BB031252061 | - | PALIKA BAZAR LANDMARK CITY KOTA324007 | KOTA | Kota | 324007 | PALIKA BAZAR LANDMARK CITY KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
123 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031116023 | - | BHATI HPCL PETROL PUMP NAGAUR341001 | NAGAURI | Nagaur | 341001 | BHATI HPCL PETROL PUMP NAGAUR341001 | 4G Router |  | CTS | 1 |  | Kuldeep ojha (9024122510) darji mohallah karni colony rathori kuwa nagaur341001 | Kuldeep ojha | 9024122510 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
124 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW015415466 | - | Sbi officer's Flats , near LIC Building ,Jodhpur 342006 | JODHPUR | Jodhpur | 342006 | Sbi officer's Flats , near LIC Building ,Jodhpur 342006 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
125 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW000603030 | - | RPSC Ajmer RPSC Ajmer 305001 RAJASTHAN305001 | AJMER | Ajmer | 305001 | RPSC Ajmer RPSC Ajmer 305001 RAJASTHAN305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
126 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031116022 | - | ADITYA HOTEL NAGAUR341001 | NAGAUR | Nagaur | 341001 | ADITYA HOTEL NAGAUR341001 | 4G Router |  | CTS | 1 |  | Kuldeep ojha (9024122510) darji mohallah karni colony rathori kuwa nagaur341001 | Kuldeep ojha | 9024122510 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
127 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603010 | - | C-1, CRPF,Kundan Nagar Ajmer305001 | AJMER | Ajmer | 305001 | C-1, CRPF,Kundan Nagar Ajmer305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
128 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NB031252007 | - | BARAN ROAD KOTA324007 | KOTA | Kota | 324007 | BARAN ROAD KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
129 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NB031252104 | - | SHOP NO. 03, RIDHI SIDHI SHOPPING MALL, 410, COMPETITION OLONY RANGBARI MAIN ROAD MAHAVEER NAGAR-III CIRCLE KOTA324007 | KOTA | Kota | 324007 | SHOP NO. 03, RIDHI SIDHI SHOPPING MALL, 410, COMPETITION OLONY RANGBARI MAIN ROAD MAHAVEER NAGAR-III CIRCLE KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
130 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG014892002 | - | SBI ATM IIT JODHPUR342005 | JODHPUR | Jodhpur | 342005 | SBI ATM IIT JODHPUR342005 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
131 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG000618009 | - | GANPATI PLAZA, BEAWAR305901 | BEAWAR | Ajmer | 305901 | GANPATI PLAZA, BEAWAR305901 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
132 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031252033 | - | STATE BANK OF INDIA, GANDHIJI KI PUL, SHRIPURA, KOTA324007 | KOTA | Kota | 324007 | STATE BANK OF INDIA, GANDHIJI KI PUL, SHRIPURA, KOTA324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
133 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BB031252065 | - | AERODRUM CIRCLE324007 | KOTA | Kota | 324007 | AERODRUM CIRCLE324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
134 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW015415022 | - | MATKI CHORAHA - JODHPUR,RAJASTHAN,342001342001 | JODHPUR | Jodhpur | 342001 | MATKI CHORAHA - JODHPUR,RAJASTHAN,342001342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
135 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW000603039 | - | Br. Code603Shreya Market, Station Road, Ajmer Shreya Market, Station Road, Ajmer Ajmer Ajmer 305001 RAJASTHAN305001 | AJMER | Ajmer | 305001 | Br. Code603Shreya Market, Station Road, Ajmer Shreya Market, Station Road, Ajmer Ajmer Ajmer 305001 RAJASTHAN305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
136 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG031116002 | - | GHANDHI CHOWK NAGAUR341001 | NAGAUR | Nagaur | 341001 | GHANDHI CHOWK NAGAUR341001 | 4G Router |  | CTS | 1 |  | Kuldeep ojha (9024122510) darji mohallah karni colony rathori kuwa nagaur341001 | Kuldeep ojha | 9024122510 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
137 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW000603033 | - | Br. Code603 Ram dental college , Ajmer Ram dental college , Ajmer Ajmer Ajmer 305001 RAJASTHAN305001 | AJMER | Ajmer | 305001 | Br. Code603 Ram dental college , Ajmer Ram dental college , Ajmer Ajmer Ajmer 305001 RAJASTHAN305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
138 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG015415484 | - | 9 MILE Mandore JODHPUR324004 | JODHPUR (MCO) | Jodhpur | 324004 | 9 MILE Mandore JODHPUR324004 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
139 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415043 | - | PALIWAL PETROL PUMP342001 | JODHPUR | Jodhpur | 342001 | PALIWAL PETROL PUMP342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
140 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW031290001 | - | STATE BANK OF INDIA NEAR BUS STAND , BAZAR ROAD, KUCHERA, DISTT. NAGAUR - 341024341024 | NAGAUR | Nagaur | 341024 | STATE BANK OF INDIA NEAR BUS STAND , BAZAR ROAD, KUCHERA, DISTT. NAGAUR - 341024341024 | 4G Router |  | CTS | 1 |  | Kuldeep ojha (9024122510) darji mohallah karni colony rathori kuwa nagaur341001 | Kuldeep ojha | 9024122510 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
141 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW000603029 | - | STATION ROAD, AJMER, RAJASTHAN, 305001305001 | AJMER | Ajmer | 305001 | STATION ROAD, AJMER, RAJASTHAN, 305001305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
142 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BW031252014 | - | 2ND ATM AT BARAN ROAD, KOTA, RAJASTHAN, 324007324007 | KOTA | Kota | 324007 | 2ND ATM AT BARAN ROAD, KOTA, RAJASTHAN, 324007324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
143 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG015415462 | - | Krishna HPCL filling station342001 | JODHPUR | Jodhpur | 342001 | Krishna HPCL filling station342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
144 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603005 | - | HPCL Petrol Pump KATCHERY ROAD305001 | AJMER PUMP AJ | Ajmer | 305001 | HPCL Petrol Pump KATCHERY ROAD305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
145 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415052 | - | RLY STATION JODHPUR342001 | JODHPUR | Jodhpur | 342001 | RLY STATION JODHPUR342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
146 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW015415467 | - | STC BSF AREA JODHPUR STC BSF AREA JODHPUR 342001 RAJASTHAN342006 | JODHPUR | Jodhpur | 342006 | STC BSF AREA JODHPUR STC BSF AREA JODHPUR 342001 RAJASTHAN342006 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
147 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415044 | - | MANGAL FILLING STATION342001 | JODHPUR | Jodhpur | 342001 | MANGAL FILLING STATION342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
148 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603007 | - | NEAR STATE BANK OF INDIA, Amjer305001 | AJMER | Ajmer | 305001 | NEAR STATE BANK OF INDIA, Amjer305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
149 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW015415030 | - | Indian Air Force Station, Vidhya Park Jodhpur342001 | JODHPUR | Jodhpur | 342001 | Indian Air Force Station, Vidhya Park Jodhpur342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
150 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG015415453 | - | RAILWAY STATION JODHPUR RAJASTAN342001 | JODHPUR | Jodhpur | 342001 | RAILWAY STATION JODHPUR RAJASTAN342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
151 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG000603008 | - | Group Centre,Crpf Campus305001 | AJMER | Ajmer | 305001 | Group Centre,Crpf Campus305001 | 4G Router |  | CTS | 1 |  | Manoj Choudhary (7414037556 )H.N. 4-A Chamunda Colony Foy sagar road Ajmer 305001 | Manoj Choudhary | 7414037556 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
152 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415046 | - | INCOME TAX OFFICE JODHPUR342001 | JODHPUR | Jodhpur | 342001 | INCOME TAX OFFICE JODHPUR342001 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
153 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1BG031252011 | - | 2ND ATM AT OM CINE PLEX324007 | KOTA | Kota | 324007 | 2ND ATM AT OM CINE PLEX324007 | 4G Router |  | CTS | 1 |  | Jai shyam malav (8118866181)- A-30, Shree ram colony opp. Sbi bank borkhera kota,324001 | Jai shyam malav | 8118866181 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
154 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NW031206005 | - | Near Bus Stand, Osian, Jodhpur342303 | OSIAN | Jodhpur | 342303 | Near Bus Stand, Osian, Jodhpur342303 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending
155 | Sandeep Prajapati | North | Advantage SB | SBI | NA | S1NG015415047 | - | SARASWATI NAGAR JODHPUR342006 | JODHPUR | Jodhpur | 342006 | SARASWATI NAGAR JODHPUR342006 | 4G Router |  | CTS | 1 |  | vinod kumar sharma (8058757649) BJS colony paota B road RTO Office Near by krishna bikaneri mishtan bhandar Jodhpur 342006 | vinod kumar sharma | 8058757649 | [6 empty] | Dispatch Pending |  |  |  | Dispatch Pending

## Sheet4 (hidden)
F | 7000 | done
L | 3000 | done
V | 1200 | done
J | 1000 | done
C | 700
T | 1000
K | 1000
G | 1000
M | 1200
S | 500
Mu | 2000
R | 5000
MO | 3000
2800