## Sheet1
Sr. No. | TermId | NW | Region | Module | Address | City | State | Gateway IP Address | ATM IP Address | SUBNET MASK | Switch URL | Primary DNS | Alternate DNS | PORT NUMBER | Date of Schedule | Date of Reschedule | Schedule Status | Reamrks | REQUEST ID FROM LHO | Date of Router Installation | Router Installation Status | Remarks | ATM Live Date | ATM Live Status | Remarks | IR Signed & Stamped date | Signed & Stampted IR Copy (Recvd/Not Recvd | HARD COPY WITH
1 | S10A001446001 | NW-1 | BPL-7 | BHOPAL | SBI MAHESHWARI COMPLEX 1ST ATM PANDHURNA | PANDHURNA | MP | 10.130.13.37 | 10.130.13.38 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5337 | 22.03.2024 |  |  |  | RM01371651 | 22.03.2024 | Done |  | 22.03.2024 | Live |  | 22.03.2024 | Received | Installation Engg.
2 | S10A000383002 | NW-1 | BPL-4 | BHOPAL | RLY STATION HOSHANGABAD | HOSHANGABAD | MP | 10.130.12.229 | 10.130.12.230 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5337 | 21.03.2024 | 23.03.2024 | software issue | Bank Dependency | RM01371641 | 21.03.2024 | Done |  | NOT LIVE | NOT LIVE | Bank Dependency | pending | pending | pending
3 | S1BB000383032 | NW-1 | BPL-4 | BHOPAL | HERO HONDA SHOW ROOM HOSHANGABAD | HOSHANGABAD | MP | 10.130.12.225 | 10.130.12.226 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5337 | 21.03.2024 |  |  |  | RM01371649 | 21.03.2024 | Done |  | 21.03.2024 | Live |  | pending | pending | pending
4 | S1BG014803232 | NW-2 | JBP-1 | JABALPUR | VEHICLE ESTATE JABALPUR | JABALPUR | MP | 10.130.13.85 | 10.130.13.86 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5337 | 21.03.2024 |  |  |  | RM01371652 | 21.03.2024 | Done |  | 22.03.2024 | Live |  | pending | pending | pending
5 | S1BW014803237 | NW-2 | JBP-1 | JABALPUR | VEHICLE FACTORY JABALPUR | JABALPUR | MP | 10.130.13.89 | 10.130.13.90 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5337 | 21.03.2024 | 23.03.2024 | power socket not available for router | Bank Dependency | RM01371660 | pending | pending |  | NOT LIVE | NOT LIVE | Bank Dependency | pending | pending | pending
6 | S1BB015656199 | NW-1 | IND-1 | INDORE | BHAWARKUWA SQUARE INDORE | Indore | MP | 10.130.8.209 | 10.130.8.210 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 02.03.2024 | 23.03.2024 | software issue | Bank Dependency | RM01364227 | 02.03.2024 | Done |  | NOT LIVE | NOT LIVE | Bank Dependency | pending | pending | pending
7 | S1NW001470003 | NW-3 | RPR-1 | RAIPUR | NEORA Tilda Raipur | RAIPUR | CG | 10.130.9.41 | 10.130.9.42 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 3556 | 01.03.2024 |  |  |  | RM01363116 | 01.03.2024 | Done |  | 01.03.2024 | Live |  | 01.03.2024 | Received | Rahul Shama
8 | S1BW015142106 | NW-3 | BSP-1 | BILASPUR | JARHABHATA CHOWK, Dist. COURT CAMPUS, BILASPUR | BILASPUR | CG | 10.130.10.45 | 10.130.10.46 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 3556 | 29.02.2024 |  |  |  | RM01363100 | 29.02.2024 | Done |  | 29.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
9 | S1BG014132266 | NW-1 | BPL-1 | BHOPAL | FOOTBALL GROUND KIRANDUL, DISTT - DANTEWADA, PIN - 494556 | BHOPAL | MP | 10.130.7.201 | 10.130.7.202 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 3556 | 29.02.2024 |  |  |  | RM01363102 | 29.02.2024 | Done |  | 29.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
10 | S1BW015656067 | NW-1 | IND-2 | INDORE | MANGAL CITY MALL | INDORE | MP | 10.130.8.249 | 10.130.8.250 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 29.02.2024 |  |  |  | RM01363125 | 29.02.2024 | Done |  | 04.03.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
11 | S10A000379002 | NW-1 | BPL-6 | BHOPAL | RAILWAY STATION HARDA | HARDA | MP | 10.130.9.89 | 10.130.9.90 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 28.02.2024 |  |  |  | RM01360089 | 28.02.2024 | Done |  | 02.03.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
12 | S1BB015656267 | NW-1 | IND-1 | INDORE | AIRPORT CAMPUS INDORE | INDORE | MP | 10.130.7.45 | 10.130.7.46 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 27.02.2024 |  |  |  | RM01361905 | 27.02.2024 | Done |  | 27.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
13 | S1BW015656405 | NW-1 | IND-1 | INDORE | CHETAK CHAMBERS. INDORE ( UNIVERCITY CAMPUS ) | INDORE | MP | 10.130.6.197 | 10.130.6.198 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 26.02.2024 |  |  |  | RM01361711 | 26.02.2024 | Done |  | 27.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
14 | S1BB015656222 | NW-1 | IND-2 | INDORE | M.G. ROAD KOTHARI MARKET SUKHSAGAR BHAWAN INDORE | INDORE | MP | 10.130.9.53 | 10.130.9.54 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.02.2024 |  |  |  | RM01361157 | 23.02.2024 | Done |  | 23.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
15 | S1BW015656224 | NW-1 | IND-2 | INDORE | C-21 MALL INDORE | INDORE | MP | 10.130.10.109 | 10.130.10.110 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 22.02.2024 |  |  |  | RM01360396 | 22.02.2024 | Done |  | 22.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
16 | S1BB003018003 | NW-1 | IND-5 | INDORE | DURGA PLAZA, UJJAIN | UJJAIN | MP | 10.130.9.57 | 10.130.9.58 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 21.02.2024 |  |  |  | RM01360091 | 22.02.2024 | Done |  | 23.02.2024 | Live |  | 11.03.2024 | Received | Rahul Shama
17 | S10A000361001 | NW-3 | RPR-4 | RAIPUR | VILL ARJUNI DHAMTARI 493773 | DHAMTARI | CG | 10.130.7.229 | 10.130.7.230 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 17.02.2024 |  |  |  | RM01353522 | 17.02.2024 | Done |  | 17.02.2024 | Live |  | 02.02.2023 | Received | Rahul Shama
18 | S1NW000320003 | NW-3 | RPR-4 | RAIPUR | SADAR ROAD BALOD 491226 | BALOD | CG | 10.130.8.245 | 10.130.8.246 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 15.02.2024 |  |  |  | RM01353542 | 15.02.2024 | Done |  | 15.02.2024 | Live |  | 15.02.2024 | Received | Rahul Shama
19 | S1BW000468006 | NW-2 | JBP-6 | JABALPUR | ARUNNAGAR , NEHRUNAGAR REWA NEAR SHARDA THIA PIN- 486001 | REWA | MP | 10.130.7.133 | 10.130.7.134 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 07.02.2024 |  |  |  | RM01353529 | 07.02.2024 | Done |  | 07.02.2024 | Live |  | 07.02.2024 | Received | Rahul Shama
20 | S1BB004510001 | NW-2 | JBP-2 | JABALPUR | MALAJKHAND VB BALAGHAT PIN -481116 | MALAJKHAND | MP | 10.130.5.193 | 10.130.5.194 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 05.02.2024 |  |  |  | RM01350907 | 07.02.2024 | Done |  | 07.02.2024 | Live |  | 07.02.2024 | Received | Rahul Shama
21 | S1NW005509001 | NW-3 | BSP-4 | BILASPUR | MAIN ROAD BATAULI,SURGUJA,CHHATTISGARH | SURGUJA | CG | 10.130.9.93 | 10.130.9.94 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 05.02.2024 |  |  |  | RM01350915 | 05.02.2024 | Done |  | 05.02.2024 | Live |  | 05.02.2024 | Received | Rahul Shama
22 | S1BB002869002 | NW-2 | JBP-3 | JABALPUR | MAIN MARKET KOTMA, DIST ANUPPUR, 484334 | KOTMA | MP | 10.130.10.133 | 10.130.10.134 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 03.02.2024 |  |  |  | RM01350908 | 03.02.2024 | Done |  | 03.02.2024 | Live |  | 03.02.2024 | Received | Rahul Shama
23 | S1NB018774001 | NW-3 | BSP-4 | BILASPUR | MAIN ROAD SHANKARGARH,Balrampur,CHHATTISGARH | BALRAMPUR | CG | 10.130.8.253 | 10.130.8.254 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 03.02.2024 |  |  |  | RM01350902 | 03.02.2024 | Done |  | 03.02.2024 | Live |  | 03.02.2024 | Received | Rahul Shama
24 | S1NW002835003 | NW-3 | RPR-3 | RAIPUR | COLLECTORATE PARISAR, DISTT - BIJAPUR, PIN - 494444 | BIJAPUR | CG | 10.130.8.205 | 10.130.8.206 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 02.02.2024 |  |  |  | RM01352109 | 02.02.2024 | Done |  | 02.02.2024 | Live |  | 02.02.2024 | Received | Rahul Shama
25 | S1BW000481003 | NW-2 | JBP-3 | JABALPUR | NEAR DISTRICT HOSPITAL, SHAHDOL, DIST SHAHDOL, 484001 | SHAHDOL | MP | 10.130.10.157 | 10.130.10.158 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 02.02.2024 |  |  |  | RM01350236 | 02.02.2024 | Done |  | 02.02.2024 | Live |  | 02.02.2024 | Received | Rahul Shama
26 | S1BB000481002 | NW-2 | JBP-3 | JABALPUR | NEAR DISTRICT HOSPITAL, SHAHDOL, DIST SHAHDOL, 484001 | SHAHDOL | MP | 10.130.10.141 | 10.130.10.142 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 02.02.2024 |  |  |  | RM01350238 | 02.02.2024 | Done |  | 02.02.2024 | Live |  | 02.02.2024 | Received | Rahul Shama
27 | S1NB000449015 | NW-3 | BSP-4 | BILASPUR | NEAR POLICE STATION KHADGAWAN,Koriya,CHHATTISGARH | KHADGAWAN | CG | 10.130.9.81 | 10.130.9.82 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 02.02.2024 |  |  |  | RM01350917 | 02.02.2024 | Done |  | 02.02.2024 | Live |  | 02.02.2024 | Received | Rahul Shama
28 | S1NB000478044 | NW-2 | JBP-2 | JABALPUR | 3RD ATM TRIPTI HOTEL GHANSOR PIN- 480997 | GHANSOR | MP | 10.130.7.41 | 10.130.7.42 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350901 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
29 | S1BG000449012 | NW-3 | BSP-4 | BILASPUR | G M OFFICE PONDI CHIRIMIRI,Manendragarh Chirimiri bharatpur,CHHATTISGARH | CHIRMIRI | CG | 10.130.9.97 | 10.130.9.98 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350220 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
30 | S1BB000449011 | NW-3 | BSP-4 | BILASPUR | PETROL PUMP HALDIBARI CHIRIMIRI,Chirimiri,Manendragarh Chirimiri bharatpur,CHHATTISGARH | CHIRMIRI | CG | 10.130.9.77 | 10.130.9.78 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350222 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
31 | S1BW030039001 | NW-1 | IND-3 | INDORE | PALSUD ROAD,RAJPUR,MADHYA PRADESH | RAJPUR | MP | 10.130.6.153 | 10.130.6.154 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01346106 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
32 | S1NB002866005 | NW-3 | RPR-3 | RAIPUR | 3RD ATM NMDC CAMPUS KIRANDUL,FOOTBALL GROUND KIRANDUL, DISTT - DANTEWADA, PIN - 494556 | KIRANDUL | CG | 10.130.9.137 | 10.130.9.138 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350894 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 01.02.2024 | Received | Rahul Shama
33 | S1NW002866003 | NW-3 | RPR-3 | RAIPUR | FOOTBALL GROUND KIRANDUL, DISTT - DANTEWADA, PIN - 494556 | KIRANDUL | CG | 10.130.9.221 | 10.130.9.222 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350894 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 01.02.2024 | Received | Rahul Shama
34 | S1NW003183003 | NW-3 | RPR-3 | RAIPUR | NEAR COFFE HOUSE BACHELI, DISTT - DANTEWADA PIN -494553 | BACHELI | CG | 10.130.9.225 | 10.130.9.226 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350913 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
35 | S1NB030031010 | NW-1 | IND-4 | INDORE | NTPC SELDA DIST KHARGONE | KHARGONE | MP | 10.130.10.145 | 10.130.10.146 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 01.02.2024 |  |  |  | RM01350251 | 01.02.2024 | Done |  | 01.02.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
36 | S1NB001349024 | NW-2 | JBP-3 | JABALPUR | PEEPAL CHOWK, NOWROZABAD, DIST UMARIA, 484660 | NOWROZABAD | MP | 10.130.10.161 | 10.130.10.162 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01350235 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
37 | S1BB000405080 | NW-2 | JBP-4 | JABALPUR | IN FRONT OF NARMADA GUEST, Katni , MADHYA PRADESH, 483880 | KATNI | MP | 10.130.10.137 | 10.130.10.138 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01350099 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 31.01.2024 | Received | Rahul Shama
38 | S1NB030027036 | NW-1 | IND-4 | INDORE | MANDLESHWAR 2ND ATM | MANDLESHWAR | MP | 10.130.9.125 | 10.130.9.126 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01346135 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
39 | S1BW015141129 | NW-3 | RPR-2 | RAIPUR | SCIENCE COLLEGE DURG PIN 491001 | DURG | CG | 10.130.9.133 | 10.130.9.134 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01351025 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
40 | S1BW030055003 | NW-1 | IND-7 | INDORE | CRPF CAMPUS, DISTT NEEMUCH | NEEMUCH | MP | 10.130.9.129 | 10.130.9.130 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01348495 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 06.02.2024 | Received | Rahul Shama
41 | S1BG001349002 | NW-2 | JBP-3 | JABALPUR | GANDHI CHOWK UMARIYA, DIST UMARIA, 484661 | UMARIA | MP | 10.130.10.129 | 10.130.10.130 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 31.01.2024 |  |  |  | RM01350233 | 31.01.2024 | Done |  | 31.01.2024 | Live |  | 31.01.2024 | Received | Rahul Shama
42 | S1BW000417004 | NW-2 | JBP-4 | JABALPUR | SARLA NAGAR MAIHAR, Satna, MADHYA PRADESH, 485771 | MAIHAR | MP | 10.130.9.201 | 10.130.9.202 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 30.01.2024 |  |  |  | RM01350105 | 30.01.2024 | Done |  | 30.01.2024 | Live |  | 31.01.2024 | Received | Rahul Shama
43 | S1BW000355041 | NW-2 | GWL-6 | GWALIOR | MYCEM CEMENT NARSINGHGARH',DAMOH,MADHYA PRADESH | NARSINGARH | MP | 10.130.9.113 | 10.130.9.114 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 30.01.2024 |  |  |  | RM01346661 | 30.01.2024 | Done |  | 30.01.2024 | Live |  | 30.01.2024 | Received | Rahul Shama
44 | S1BG002864003 | NW-3 | BSP-3 | BILASPUR | SBI ATM CHAPLE KHARSIA ROAD PIN 496661 | CHAPLE KHARSIA | CG | 10.130.7.237 | 10.130.7.238 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 30.01.2024 |  |  |  | RM01347280 | 30.01.2024 | Done |  | 30.01.2024 | Live |  | 20.01.2024 | Received | Rahul Shama
45 | S1BW061185153 | NW-3 | RPR-1 | RAIPUR | RaMTAKRI, MHOU NEEMUCH RAOD MANDSAUR | RAIPUR | CG | 10.130.11.1 | 10.130.11.2 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 30.01.2024 |  |  |  | RM01346128 | 30.01.2024 | Done |  | 30.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
46 | S1BW015142077 | NW-3 | BSP-1 | BILASPUR | HIGHCOURT RESIDENTIAL CHAKARBHATA,CHHATTISGARH | CHAKARBHATA | CG | 10.130.10.49 | 10.130.10.50 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 29.01.2024 |  |  |  | RM01344417 | 29.01.2024 | Done |  | 29.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
47 | S1BB000460018 | NW-3 | BSP-3 | BILASPUR | SBI ATM URDARA POLICE COLONY RAIGARH PIN 496001 | RAIGARH | CG | 10.130.9.209 | 10.130.9.210 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 25.01.2024 |  |  |  | RM01347289 | 25.01.2024 | Done |  | 25.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
48 | S10A000460003 | NW-3 | BSP-3 | BILASPUR | SBI ATM NEAR COLLECTRATE RAIGARH PIN 496001 | RAIGARH | CG | 10.130.9.37 | 10.130.9.38 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348079 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
49 | S1BB000460007 | NW-3 | BSP-3 | BILASPUR | SBI ATM NEAR COLLECTRATE RAIGARH PIN 496001 | RAIGARH | CG | 10.130.9.205 | 10.130.9.206 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348081 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
50 | S1BB000422002 | NW-1 | IND-7 | INDORE | RAMTAKRI, MHOU NEEMUCH RAOD MANDSAUR | MANDSOUR | MP | 10.130.10.17 | 10.130.10.18 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348131 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
51 | S1BB000422003 | NW-1 | IND-7 | INDORE | SBI MAIN BRANCH, MANDSAUR | MANDSOUR | MP | 10.130.10.13 | 10.130.10.14 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348132 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
52 | S1BW000422015 | NW-1 | IND-7 | INDORE | BPL CHOURAHA, MANDSOUR | MANDSOUR | MP | 10.130.6.193 | 10.130.6.194 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348136 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
53 | S1BW000436014 | NW-2 | JBP-5 | JABALPUR | MAHAJANI WARD, NARSINGHPUR, Pin Code - 487001 | NARSINGPUR | MP | 10.130.6.165 | 10.130.6.166 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348139 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 14.02.2024 | Received | Rahul Shama
54 | S1BW000436012 | NW-2 | JBP-5 | JABALPUR | MAHAJANI WARD, NARSINGHPUR, Pin Code - 487001 | NARSINGPUR | MP | 10.130.9.197 | 10.130.9.198 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348141 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 14.02.2024 | Received | Rahul Shama
55 | S1BW000436013 | NW-2 | JBP-5 | JABALPUR | MAHAJANI WARD, NARSINGHPUR, Pin Code - 487001 | NARSINGPUR | MP | 10.130.6.169 | 10.130.6.170 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348142 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
56 | S1BB000468002 | NW-2 | JBP-6 | JABALPUR | GURH CHAURAHA, PTS PETROL PUMP REWA PIN- 486001 | REWA | MP | 10.130.7.129 | 10.130.7.130 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348147 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
57 | S1NW000468011 | NW-2 | JBP-6 | JABALPUR | VENKAT ROAD,IN FROUNT OF SURYA HOTEL, REWA PIN-486001 | REWA | MP | 10.130.9.17 | 10.130.9.18 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348150 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 16.02.2024 | Received | Rahul Shama
58 | S1BW015141141 | NW-3 | RPR-2 | RAIPUR | BORIA GATE, BHILAI PIN 490001 | BHILAI | CG | 10.130.10.77 | 10.130.10.78 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348203 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 16.02.2024 | Received | Rahul Shama
59 | S1BB015141065 | NW-3 | RPR-2 | RAIPUR | BSP AREA BHILAI 490001 | BHILAI | CG | 10.130.10.81 | 10.130.10.82 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348205 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
60 | S1BB000468003 | NW-2 | JBP-6 | JABALPUR | NEAR KUSHABHAU THAKRE HOSPITAL,BICHHIYA MARKETING COMPLEX PIN- 486001 | REWA | MP | 10.130.7.121 | 10.130.7.122 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348206 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
61 | S1NW000468010 | NW-2 | JBP-6 | JABALPUR | UNIVERSITY STADIUM COMPLEX , SIRMAUR ROAD REWA PIN - 486001 | REWA | MP | 10.130.7.125 | 10.130.7.126 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 24.01.2024 |  |  |  | RM01348529 | 24.01.2024 | Done |  | 24.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
62 | S1BB000421004 | NW-2 | JBP-2 | JABALPUR | LALIPUR CHOWK SBI MANDLA PIN- 481661 | MANDLA | MP | 10.130.7.17 | 10.130.7.18 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.01.2024 |  |  |  | RM01346116 | 23.01.2024 | Done |  | 23.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
63 | S1BB000421003 | NW-2 | JBP-2 | JABALPUR | MUNCIPAL CORPORATION MANDLA PIN 481661 | MANDLA | MP | 10.130.6.9 | 10.130.6.10 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.01.2024 |  |  |  | RM01346121 | 23.01.2024 | Done |  | 23.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
64 | S1BW016112035 | NW-2 | JBP-5 | JABALPUR | SINGHAI PETROL PUMP,Civil Line, Sagar Pin Code -470001 | SAGAR | MP | 10.130.7.33 | 10.130.7.34 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.01.2024 |  |  |  | RM01347297 | 23.01.2024 | Done |  | 23.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
65 | S1BW016112036 | NW-2 | JBP-5 | JABALPUR | SINGHAI PETROL PUMP,Civil Line, Sagar Pin Code -470001 | SAGAR | MP | 10.130.7.37 | 10.130.7.38 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.01.2024 |  |  |  | RM01347298 | 23.01.2024 | Done |  | 23.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
66 | S1BW061185056 | NW-3 | RPR-1 | RAIPUR | NEAR RAM KRISHNA CARE HOSPITAL RAIPUR 492001 | RAIPUR | CG | 10.130.8.69 | 10.130.8.70 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 23.01.2024 |  |  |  | RM01347299 | 23.01.2024 | Done |  | 23.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
67 | S1BW015142100 | NW-3 | BSP-1 | BILASPUR | MAHIMA COMPLEX VYPAR VIHAR BILASPUR,CHHATTISGARH | BILASPUR | CG | 10.130.9.61 | 10.130.9.62 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346093 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
68 | S1BW015142094 | NW-3 | BSP-1 | BILASPUR | MAHIMA COMPLEX VYPAR VIHAR BILASPUR,CHHATTISGARH | BILASPUR | CG | 10.130.9.65 | 10.130.9.66 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346094 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
69 | S1BB014803224 | NW-2 | JBP-1 | JABALPUR | PARIJAT BUILDING, DAMOH NAKA, JABALPUR MADHYA PRADESH, 482001 | JABALPUR | MP | 10.130.10.29 | 10.130.10.30 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346111 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
70 | S1BW014803198 | NW-2 | JBP-1 | JABALPUR | BALDEO BAGH CHOWK, NIWARDGANJ, JABALPUR MADHYA PRADESH, 482001 | JABALPUR | MP | 10.130.7.21 | 10.130.7.22 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346113 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 09.02.2024 | Received | Rahul Shama
71 | S1BW061185136 | NW-3 | RPR-1 | RAIPUR | SBI APARTMENT BHAGAT SINGH CHOWK CIVIL LINES RAIPUR 492001 | RAIPUR | CG | 10.130.9.13 | 10.130.9.14 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346124 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
72 | S1BB061185165 | NW-3 | RPR-1 | RAIPUR | BEHIND SBI ZONAL OFFICE BYRON BAZAR 492001 | BAYRON BAZAR | CG | 10.130.10.253 | 10.130.10.254 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346127 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
73 | S10A000355006 | NW-2 | GWL-6 | GWALIOR | SANMATI PALACE, DAMOH,MADHYA PRADESH | DAMOH | MP | 10.130.9.109 | 10.130.9.110 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 20.01.2024 |  |  |  | RM01346658 | 20.01.2024 | Done |  | 20.01.2024 | Live |  | 20.01.2024 | Received | Rahul Shama
74 | S10A000355003 | NW-2 | GWL-6 | GWALIOR | NEW COLLECTORATE',DAMOH,MADHYA PRADESH | DAMOH | MP | 10.130.7.213 | 10.130.7.214 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01344619 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
75 | S1BG030381037 | NW-1 | IND-3 | INDORE | M G ROAD,DHAR,MADHYA PRADESH | DHAR | MP | 10.130.6.161 | 10.130.6.162 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01344627 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
76 | S1NW000355043 | NW-2 | GWL-6 | GWALIOR | COLLECTORATE DAMOH',DAMOH,MADHYA PRADESH | DAMOH | MP | 10.130.10.169 | 10.130.10.170 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01344620 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
77 | S1BW014803194 | NW-2 | JBP-1 | JABALPUR | DURGA COLONY, SANJIVANI NAGAR, JABALPUR, MADHYA PRADESH, 482003 | JABALPUR | MP | 10.130.10.25 | 10.130.10.26 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01345413 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
78 | S1BW014803239 | NW-2 | JBP-1 | JABALPUR | SAMDARIYA ABHINANDAN, DAMOH NAKAMADHYA PRADESH, 482001 | JABALPUR | MP | 10.130.10.21 | 10.130.10.22 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01346110 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
79 | S1BB061185166 | NW-3 | RPR-1 | RAIPUR | NEAR CIVIL LINES NEAR OLD PHQ RAIPUR 492001 | RAIPUR | CG | 10.130.8.89 | 10.130.8.90 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01346129 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
80 | S1BW015142085 | NW-3 | BSP-1 | BILASPUR | SAIFER SCHOOL BILASPUR ,CHHATTISGARH | BILASPUR | CG | 10.130.9.5 | 10.130.9.6 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01344617 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 13.02.2024 | Received | Rahul Shama
81 | S10B000355005 | NW-2 | GWL-6 | GWALIOR | DAMOH HOSP AREA 2ND',DAMOH,MADHYA PRADESH | DAMOH | MP | 10.130.10.105 | 10.130.10.106 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01346096 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
82 | S10A000355002 | NW-2 | GWL-6 | GWALIOR | DAMOH CITY',DAMOH,MADHYA PRADESH | DAMOH | MP | 10.130.10.101 | 10.130.10.102 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 19.01.2024 |  |  |  | RM01346095 | 19.01.2024 | Done |  | 19.01.2024 | Live |  | 19.01.2024 | Received | Rahul Shama
83 | S1BB014803230 | NW-2 | JBP-1 | JABALPUR | NIHALCHAND COMPLEX PETROL, JABALPUR, MADHYA PRADESH, 482001 | JABALPUR | MP | 10.130.10.33 | 10.130.10.34 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 18.01.2024 |  |  |  | RM01345412 | 18.01.2024 | Done |  | 18.01.2024 | Live |  | 18.01.2024 | Received | Rahul Shama
84 | S1NB030381046 | NW-1 | IND-3 | INDORE | DISTRICT COURT CAMPUS, DHAR,MADHYA PRADESH | DHAR | MP | 10.130.9.85 | 10.130.9.86 | 255.255.255.252 | switch12.onlinesbi.com | 192.168.253.151 | 192.168.252.51 | 5336 | 18.01.2024 |  |  |  | RM01344624 | 18.01.2024 | Done |  | 18.01.2024 | Live |  | 18.01.2024 | Received | Rahul Shama

## Sheet4
Row Labels | Count of TermId
NW-1 | 20
BPL-1 | 1
BPL-4 | 2
BPL-6 | 1
IND-1 | 3
IND-2 | 3
IND-3 | 3
IND-4 | 2
IND-5 | 1
IND-7 | 4
NW-2 | 34
GWL-6 | 6
JBP-1 | 7
JBP-2 | 4
JBP-3 | 5
JBP-4 | 2
JBP-5 | 5
JBP-6 | 5
NW-3 | 29
BSP-1 | 5
BSP-3 | 4
BSP-4 | 5
RPR-1 | 6
RPR-2 | 3
RPR-3 | 4
RPR-4 | 2
Grand Total | 83